## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I under AKIPUR W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001897/2022-2023 | 6380 / EMD | 14/08/2022 | 13/09/2022 | A.S. ENTERPRISE | 13.05 | 9.86 | 75.56 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.II under AKIPUR W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001896/2022-2023 | 6447 / EMD | 14/08/2022 | 13/09/2022 | M/S GHOSH ENTERPRISE | 13.04 | 9.86 | 75.64 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 2309/BD | 03/08/2022 | 03/08/2022 | Resource Division | 11.42 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1100/BD | 06/04/2023 | 06/04/2023 | Resource Division | 11.42 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Akipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000749/2022-2023 | 3374/BD | 18/11/2022 | 16/02/2023 | SUPER SKILL. | 145.01 | 105.64 | 72.85 | 50
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Acceptance cum work order for Balance FHTC works and Eucalyptus Bullah Pilling with earth filling in different location for protection of DI / UPVC distribution Pipe line for Augmentation of Akipur water supply scheme in Basirhat - II Block under Basirhat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001760/2023-2024 | 512/BD | 20/02/2024 | 21/03/2024 | SUPER SKILL. | 41.71 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Akipur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000103/2023-2024 | 548/CDD | 02/06/2023 | 01/07/2024 | UTTAM KUMAR CHATTERJEE | 21.56 | 10.76 | 49.92 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Acceptance cum work order for Balance work of Providing FHTC (Functional Household Tap Connection) by Augmentation For Akipur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District within Basirhat Sub-Division under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2025-2026 | 2000/BD | 17/06/2025 | 12/02/2026 | M/S MITRA CONSTRUCTION. | 56.17 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Akipur to accommodate FHTC | SM/11533 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Taranipur zone - I W/S Scheme (50.0 m3/hr) at Swarupnagar Block and Akhipur W/S Scheme (33.375m3/hr) at Basirhat - II Block under Basirhat Sub division, PHE Dte of Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2025-2026 | 2022/BD | 18/06/2025 | 16/10/2025 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 19.65 | 0 | 0 | 70
Total | [13 empty] | 333.03 | 136.12 | 40.87