## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayagharia Zone- II water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002957/2021-2022 | 534/BON | 03/11/2021 | 24/11/2021 | PRABIR KUMAR MONDAL. | 2.52 | 2.49 | 98.95 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Laying of badly damaged distribution pipe line and others allied for widening Panchayet Road from Chhaygharia Ajay Mondal's House to Khedapara F.P School to Trimonipara at Chhaygharia (Zone-II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000626/2022-2023 | 411/Bon | 23/08/2022 | 07/09/2022 | PRABIR KUMAR MONDAL. | 4.55 | 3.39 | 74.42 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-II) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002771/2021-2022 | 124/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000822/2022-2023 | 3601/BD | 09/12/2022 | 09/03/2023 | M/S B.N ENTERPRISE | 152.03 | 151.24 | 99.48 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 3696/BD | 14/12/2022 | 14/12/2022 | Resource Division | 51.36 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 3661/BD | 13/12/2022 | 13/12/2022 | Resource Division | 8.27 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-II) (Replacement) under Chhaigharia W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer | Junior Engineer | ORD/002036/2022-2023 | 32/EMD | 03/01/2023 | 02/02/2023 | M/S. MANABESH ROY | 22.15 | 16.02 | 72.31 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-II) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1545/BD | 19/05/2023 | 18/06/2023 | NEW MA TARA ENTERPRISE. | 15.85 | 13.47 | 85 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Chhaygharia Zone-II Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000899/2023-2024 | 2797/BD | 12/09/2023 | 11/09/2025 | JOY HIND TUBEWELLS. | 91.85 | 23.41 | 25.48 | 60
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2024-2025 | 2357/BD | 20/08/2024 | 29/09/2025 | B.S.ENTERPRISE. (BASIRHAT) | 45.95 | 4.58 | 9.97 | 15
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001552/2023-2024 | 38/BD | 04/01/2024 | 27/01/2024 | M/S SANJAY ADHIKARI | 12 | 11.94 | 99.56 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Chhaygharia (Zone-II) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000645/2024-2025 | 3169/BD | 18/11/2024 | 17/05/2025 | PRABIR KUMAR MONDAL. | 24.89 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Chhaygharia (Zone-II) W/S Scheme under Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001263/2024-2025 | 1505/Bon | 30/12/2024 | 29/01/2025 | R.A. ENTERPRISE. | 4.6 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-II) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. |  |  | ORD/000083/2025-2026 | 538/Bon | 23/04/2025 | 30/04/2025 | ELDORADO | 0.55 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC | SM/11535 | Augmentation | Quotation for New service connection at P.H.No- OHR ,Zone - II of Chhaygharia water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/02465/2024-2025 | BP-209 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.11 | 0 | 0 | 0
Total | [13 empty] | 443.66 | 229.51 | 51.73