## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 2403/BD | 17/08/2022 | 15/11/2022 | R.K.MANDAL & CO. | 239.51 | 236.33 | 98.67 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Formal work order for for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 2402/BD | 17/08/2022 | 15/11/2022 | M/S PROGATI ENTERPRISE. | 238.52 | 236.38 | 99.1 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of BOUTHAKURANI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002688/2021-2022 | 230/HSD | 02/02/2022 | 17/02/2022 | UMWELT ENGINEER PVT.LTD. | 4.81 | 4.81 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2470/BD | 24/08/2022 | 24/08/2022 | Resource Division | 8.3 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 3365/BD | 17/11/2022 | 17/11/2022 | Resource Division | 3.05 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001175/2022-2023 | 788/BD | 13/03/2023 | 12/04/2023 | M/S DATTA ENTERPRISE. | 47.05 | 38.83 | 82.53 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001176/2022-2023 | 789/BD | 13/03/2023 | 12/04/2023 | M/S DATTA ENTERPRISE. | 47.04 | 37.49 | 79.69 | 1
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Bouthakurani W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001968/2022-2023 | 1282/EMD | 28/03/2023 | 27/04/2023 | SINHA ELECTRICALS | 66.26 | 57.89 | 87.36 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Additional Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000254/2023-2024 | 780/HSD | 13/07/2023 | 23/07/2023 | SHYAM SUNDAR DAS. | 0.55 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000849/2023-2024 | 2657/BD | 01/09/2023 | 01/10/2023 | R.K.MANDAL & CO. | 80.57 | 80.45 | 99.86 | 81
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-IIblock under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000719/2023-2024 | 2472/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 26.97 | 21.39 | 79.29 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 3 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000250/2023-2024 | 776/HSD | 13/07/2023 | 23/07/2023 | PRITAM MUKHOPADHYAY. | 0.73 | 0.73 | 99.85 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer |  | ORD/000255/2023-2024 | 781/HSD | 13/07/2023 | 23/07/2023 | PRITAM MUKHOPADHYAY. | 0.6 | 0.6 | 99.6 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000253/2023-2024 | 779/HSD | 13/07/2023 | 23/07/2023 | NURJAHAN ENTERPRISE. | 0.79 | 0.79 | 100 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000256/2023-2024 | 782/HSD | 13/07/2023 | 23/07/2023 | NURJAHAN ENTERPRISE. | 0.93 | 0.92 | 98.93 | 100
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 4 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000258/2023-2024 | 784/HSD | 13/07/2023 | 23/07/2023 | SHYAM SUNDAR DAS. | 0.71 | 0.7 | 98.96 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Sandeshkhali and Bouthakurani (Z-II) w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000791/2024-2025 | 3332/BD | 28/11/2024 | 27/01/2025 | UTPAL CONSTRUCTION & CO. | 63.3 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Bouthakurani water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2024-2025 | 630/HSD | 12/06/2024 | 22/06/2024 | PRITAM MUKHOPADHYAY. | 1.02 | 1 | 98.06 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-3 & 4 in connection with Augmentation for Bouthakurani water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2024-2025 | 631/HSD | 12/06/2024 | 22/06/2024 | PRITAM MUKHOPADHYAY. | 1.02 | 1.01 | 99.04 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Dholkhali Mouza in connection with Augmentation of Bouthakurani water supply scheme (Z- I), Sandeskhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001531/2024-2025 | 386/HSD | 10/02/2025 | 20/02/2025 | HASAN ENTERPRISE | 0.97 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/001535/2024-2025 | 390/HSD | 10/02/2025 | 20/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
22 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for 1 no. pump connection at PH No.-5 in connection with Augmentation for Bouthakuranii (Z-I) water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001305/2024-2025 | 151/HSD | 27/01/2025 | 06/02/2025 | PRITAM MUKHOPADHYAY. | 0.73 | 0 | 0 | 100
23 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Supply and installation of 100 & 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001470/2024-2025 | 344/HSD | 06/02/2025 | 16/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.6 | 0 | 0 | 100
24 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-3 | Assistant Engineer | Junior Engineer | ORD/001890/2024-2025 | 532/HSD | 10/03/2025 | 20/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0 | 0 | 100
25 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-2 | Assistant Engineer | Junior Engineer | ORD/000174/2025-2026 | 1006/HSD | 04/06/2025 | 14/06/2025 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 0 | 100
26 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001375/2024-2025 | 242/HSD | 30/01/2025 | 09/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.84 | 0 | 0 | 100
27 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-1 | Assistant Engineer | Junior Engineer | ORD/001442/2024-2025 | 320/HSD | 04/02/2025 | 14/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 0 | 100
28 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Providing Functional household tap connection at Tushkhali Harasit Smriti MSK, Purba Bouthakurani FP School and Dholkhali Dakshinpara SSK within the command area of Tushkhali and Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000128/2025-2026 | 952/HSD | 29/05/2025 | 08/06/2025 | M/S K.B.ENTERPRISE. | 0.91 | 0 | 0 | 100
29 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Special repair & maintenance of different dia UPVC pipe line at different places in connection with augmentation of Bouthakurani w/s Scheme (Z-II), Sandeskhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. Phase-4 | Assistant Engineer | Junior Engineer | ORD/000275/2025-2026 | 1485/HSD | 14/07/2025 | 24/07/2025 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0 | 0 | 100
30 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Providing Functional tap household connection at Bouthakurani Dakshinpara FP School and Tongtala Adibasi FP School within the command area of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000282/2025-2026 | 1492/HSD | 14/07/2025 | 24/07/2025 | M/S RAJPATH CONSTRUCTION. | 0.61 | 0 | 0 | 100
31 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001607/2024-2025 | 471/HSD | 28/02/2025 | 10/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0 | 0 | 100
32 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/001441/2024-2025 | 319/HSD | 04/02/2025 | 14/02/2025 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0 | 0 | 100
Total | [13 empty] | 843.05 | 719.33 | 85.32