## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of BOUTHAKURANI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002688/2021-2022 | 230/HSD | 02/02/2022 | 17/02/2022 | UMWELT ENGINEER PVT.LTD. | 4.81 | 4.81 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 3365/BD | 17/11/2022 | 17/11/2022 | Resource Division | 3.05 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 2403/BD | 17/08/2022 | 15/11/2022 | R.K.MANDAL & CO. | 239.51 | 236.33 | 98.67 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001175/2022-2023 | 788/BD | 13/03/2023 | 12/04/2023 | M/S DATTA ENTERPRISE. | 47.05 | 38.83 | 82.53 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001176/2022-2023 | 789/BD | 13/03/2023 | 12/04/2023 | M/S DATTA ENTERPRISE. | 47.04 | 37.49 | 79.69 | 1
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Bouthakurani W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001968/2022-2023 | 1282/EMD | 28/03/2023 | 27/04/2023 | SINHA ELECTRICALS | 66.26 | 57.89 | 87.36 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Additional Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000254/2023-2024 | 780/HSD | 13/07/2023 | 23/07/2023 | SHYAM SUNDAR DAS. | 0.55 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Formal work order for for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 2402/BD | 17/08/2022 | 15/11/2022 | M/S PROGATI ENTERPRISE. | 238.52 | 236.38 | 99.1 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 3 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000250/2023-2024 | 776/HSD | 13/07/2023 | 23/07/2023 | PRITAM MUKHOPADHYAY. | 0.73 | 0.73 | 99.85 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer |  | ORD/000255/2023-2024 | 781/HSD | 13/07/2023 | 23/07/2023 | PRITAM MUKHOPADHYAY. | 0.6 | 0.6 | 99.6 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 4 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000258/2023-2024 | 784/HSD | 13/07/2023 | 23/07/2023 | SHYAM SUNDAR DAS. | 0.71 | 0.7 | 98.96 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-IIblock under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000719/2023-2024 | 2472/BD | 18/08/2023 | 17/09/2023 | M/S DATTA ENTERPRISE. | 26.97 | 21.39 | 79.29 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000849/2023-2024 | 2657/BD | 01/09/2023 | 01/10/2023 | R.K.MANDAL & CO. | 80.57 | 80.45 | 99.86 | 81
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2470/BD | 24/08/2022 | 24/08/2022 | Resource Division | 8.3 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Sandeshkhali and Bouthakurani (Z-II) w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000791/2024-2025 | 3332/BD | 28/11/2024 | 27/01/2025 | UTPAL CONSTRUCTION & CO. | 63.3 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000253/2023-2024 | 779/HSD | 13/07/2023 | 23/07/2023 | NURJAHAN ENTERPRISE. | 0.79 | 0.79 | 100 | 100
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000256/2023-2024 | 782/HSD | 13/07/2023 | 23/07/2023 | NURJAHAN ENTERPRISE. | 0.93 | 0.92 | 98.93 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Bouthakurani water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2024-2025 | 630/HSD | 12/06/2024 | 22/06/2024 | PRITAM MUKHOPADHYAY. | 1.02 | 1 | 98.06 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-3 & 4 in connection with Augmentation for Bouthakurani water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2024-2025 | 631/HSD | 12/06/2024 | 22/06/2024 | PRITAM MUKHOPADHYAY. | 1.02 | 1.01 | 99.04 | 100
20 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme For Bouthakurani to Accommodate FHTC. | SM/11536 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Dholkhali Mouza in connection with Augmentation of Bouthakurani water supply scheme (Z- I), Sandeskhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001531/2024-2025 | 386/HSD | 10/02/2025 | 20/02/2025 | HASAN ENTERPRISE | 0.97 | 0 | 0 | 0
Total | [13 empty] | 832.74 | 719.33 | 86.38