## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1559/BD | 23/05/2023 | 23/05/2023 | Resource Division | 7.62 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Daora, Diara & Gokulpur W/S Scheme, District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000828/2022-2023 | 34/EMD | 03/01/2023 | 02/02/2023 | AHALYA ENGINEERING WORKS | 70.02 | 0 | 0 | 76
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.23 to 29.02.24) | Assistant Engineer | Junior Engineer | ORD/001226/2023-2024 | 476/HAB | 31/08/2023 | 29/02/2024 | M/S SUKANTA ENTERPRISE. | 0.86 | 0 | 0 | 10
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | construction of Service Road (55 Mtr. Length and 2 Mtr. Width) for Pump House No:1 of Deora Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. |  |  | ORD/000196/2024-2025 | 689/HAB | 24/07/2024 | 08/08/2024 | M/S SUKANTA ENTERPRISE. | 3.52 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Acceptance cum work order for Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Deora W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000160/2024-2025 | 1798/BD | 01/07/2024 | 31/07/2024 | M/S SUKANTA ENTERPRISE. | 5.27 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Deora Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 1191/BD | 19/04/2023 | 18/07/2023 | CHANDA CONSTRUCTION. | 267.73 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Daora to accommodate FHTC | SM/11537 | Augmentation | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Deora water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000974/2023-2024 | 2780/BD | 11/09/2023 | 10/11/2023 | M/S SUKANTA ENTERPRISE. | 39.1 | 0 | 0 | 80
Total | [13 empty] | 394.12 | 0 | 0