## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002907/2021-2022 | 527/Bon | 01/11/2021 | 22/11/2021 | ACHINTA KUMAR HALDER. | 2.52 | 2.47 | 98.19 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002786/2021-2022 | 136/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 3.62 | 99.54 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 3694/BD | 14/12/2022 | 14/12/2022 | Resource Division | 26.68 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 3713/BD | 15/12/2022 | 15/12/2022 | Resource Division | 11.89 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (New) under Kola W/S Scheme, Block-Barasat-II, District of 24 Pgs. (N). |  |  | ORD/001264/2023-2024 | 4933/EMD | 18/08/2023 | 17/09/2023 | BARISAL TRADING CO. | 22.15 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Emergency laying of wash out pipe line and others allied works from Kola Pump House No-I to nearest Baor at Adibasi Para at Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 383/Bon | 05/08/2022 | 17/08/2022 | ACHINTA KUMAR HALDER. | 1.1 | 1.08 | 98.63 | 1
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Supply fitting fixing of change over switch at P.H.No-I & II ,Zone-I of Ghatpatila and P.H.No- I & II of Kola W/S Scheme under EMSD-I, P.H.E. Dte. Dist.-24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/001819/2023-2024 | 1814/EMSD-I | 18/08/2023 | 02/09/2023 | SUNRISE ENGINEERING CORPORATION | 0.86 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001758/2023-2024 | 524/BD | 20/02/2024 | 21/03/2024 | DEL DELTA CONSTRUCTION | 13.55 | 10.71 | 79.09 | 85
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kola Water Supply Scheme, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001029/2022-2023 | 264/BD | 01/02/2023 | 02/05/2023 | MONDAL PRECISION PVT.LTD | 330.92 | 326.52 | 98.67 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kola Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001115/2023-2024 | 2938/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 15.11 | 93.74 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Renovation of 34 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Kola water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001541/2023-2024 | 12/BD | 02/01/2024 | 02/03/2024 | PUSPA ENTERPRISE. | 38.78 | 31.28 | 80.67 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Boundary wall at 2nd T/W site and Construction of Approach Road at Head work site and 2nd T/W site under Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001773/2023-2024 | 624/BD | 28/02/2024 | 22/02/2025 | ONKAR ENTERPRISE. | 11.17 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Special repairing work for smooth supply of water at the tail end of Jitpur (JL No. 32) and Kashipur (JL No. 25) Mouza to convert the mouzas in to Swajal Gram in connection with Augmentation Work at Kola W/S Scheme under Bagdah Block within the jurisdiction of Bongaon Sub-Division under, Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000401/2025-2026 | 822/Bon | 30/06/2025 | 14/08/2025 | ADIL CONSTRUCTION | 4.9 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Pump Connection of the newly sunk Replacement Tube-well, Special repairing, Road Restoration and allied works in connection with Augmentation Work at Kola W/S Scheme under Bagdah Block within the jurisdiction of Bongaon Sub-Division under, Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2025-2026 | 851/Bon | 03/07/2025 | 17/08/2025 | ACHINTA KUMAR HALDER. | 4.5 | 0 | 0 | 100
Total | [13 empty] | 488.76 | 390.8 | 79.96