## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002907/2021-2022 | 527/Bon | 01/11/2021 | 22/11/2021 | ACHINTA KUMAR HALDER. | 2.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002786/2021-2022 | 136/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2022-2023 | 3694/BD | 14/12/2022 | 14/12/2022 | Resource Division | 26.68 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 3713/BD | 15/12/2022 | 15/12/2022 | Resource Division | 11.89 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (New) under Kola W/S Scheme, Block-Barasat-II, District of 24 Pgs. (N). |  |  | ORD/001264/2023-2024 | 4933/EMD | 18/08/2023 | 17/09/2023 | BARISAL TRADING CO. | 22.15 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Emergency laying of wash out pipe line and others allied works from Kola Pump House No-I to nearest Baor at Adibasi Para at Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 383/Bon | 05/08/2022 | 17/08/2022 | ACHINTA KUMAR HALDER. | 1.1 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Supply fitting fixing of change over switch at P.H.No-I & II ,Zone-I of Ghatpatila and P.H.No- I & II of Kola W/S Scheme under EMSD-I, P.H.E. Dte. Dist.-24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/001819/2023-2024 | 1814/EMSD-I | 18/08/2023 | 02/09/2023 | SUNRISE ENGINEERING CORPORATION | 0.86 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001758/2023-2024 | 524/BD | 20/02/2024 | 21/03/2024 | DEL DELTA CONSTRUCTION | 13.55 | 0 | 0 | 85
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kola Water Supply Scheme, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001029/2022-2023 | 264/BD | 01/02/2023 | 02/05/2023 | MONDAL PRECISION PVT.LTD | 330.92 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kola Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001115/2023-2024 | 2938/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Renovation of 34 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Kola water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001541/2023-2024 | 12/BD | 02/01/2024 | 02/03/2024 | PUSPA ENTERPRISE. | 38.78 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kola to accommodate FHTC | SM/11538 | Augmentation | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Boundary wall at 2nd T/W site and Construction of Approach Road at Head work site and 2nd T/W site under Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001773/2023-2024 | 624/BD | 28/02/2024 | 22/02/2025 | ONKAR ENTERPRISE. | 11.17 | 0 | 0 | 100
Total | [13 empty] | 479.37 | 0 | 0