## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Malidah water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002970/2021-2022 | 526/ BON | 01/11/2021 | 22/11/2021 | TAPAN GHOSH. | 2.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002785/2021-2022 | 140/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 3686/BD | 14/12/2022 | 14/12/2022 | Resource Division | 12.95 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 3712/BD | 15/12/2022 | 15/12/2022 | Resource Division | 1.79 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) under Ghatpatila W/S Scheme, Kola W/S Scheme (P/H-I &II) & Malidah W/S Scheme (P/H-I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 08) |  |  | ORD/002530/2023-2024 | 35EMD | 23/08/2023 | 22/09/2023 | SUNRISE ENGINEERING CORPORATION | 65.84 | 0 | 0 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Malidah Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000774/2022-2023 | 3471/BD | 01/12/2022 | 01/03/2023 | R.K.MANDAL & CO. | 243.9 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Sinking of 2 (two) nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Malidah Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001013/2023-2024 | 2830/BD | 15/09/2023 | 14/11/2023 | DHELA BABA ENTERPRISE | 32.28 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 4407/BD | 10/11/2023 | 09/01/2024 | BHABANI ENTERPRISE. | 11.49 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001486/2023-2024 | 4465/BD | 21/11/2023 | 14/12/2023 | KAMAL HALDER. | 7.15 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Malidah W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000042/2025-2026 | 1541/BD | 15/05/2025 | 12/09/2025 | NISHITH BANERJEE | 31.89 | 0 | 0 | 0
Total | [13 empty] | 413.54 | 0 | 0