## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Malidah water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002970/2021-2022 | 526/ BON | 01/11/2021 | 22/11/2021 | TAPAN GHOSH. | 2.52 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002785/2021-2022 | 140/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 3686/BD | 14/12/2022 | 14/12/2022 | Resource Division | 12.95 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 3712/BD | 15/12/2022 | 15/12/2022 | Resource Division | 1.79 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) under Ghatpatila W/S Scheme, Kola W/S Scheme (P/H-I &II) & Malidah W/S Scheme (P/H-I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/002530/2023-2024 | 35EMD | 23/08/2023 | 22/09/2023 | SUNRISE ENGINEERING CORPORATION | 65.84 | 0 | 0 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Malidah Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000774/2022-2023 | 3471/BD | 01/12/2022 | 01/03/2023 | R.K.MANDAL & CO. | 243.9 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Sinking of 2 (two) nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Malidah Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001013/2023-2024 | 2830/BD | 15/09/2023 | 14/11/2023 | DHELA BABA ENTERPRISE | 32.28 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 4407/BD | 10/11/2023 | 09/01/2024 | BHABANI ENTERPRISE. | 11.49 | 0 | 0 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001486/2023-2024 | 4465/BD | 21/11/2023 | 14/12/2023 | KAMAL HALDER. | 7.15 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Malidah W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000042/2025-2026 | 1541/BD | 15/05/2025 | 12/09/2025 | NISHITH BANERJEE | 31.89 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Repair and renovation works of 250cum capacity 20mtr. staging height R.C.C. over Head Reservoir for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2024-2025 | 3404/BD | 04/12/2024 | 02/06/2025 | PRABIR KUMAR MONDAL. | 7.9 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Malidah to accommodate FHTC | SM/11539 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying and repair of UPVC pipe and allied works in connection with Augmentation work at Malidah W/S Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000861/2024-2025 | 3386/BD | 03/12/2024 | 03/03/2025 | VAI ENTERPRISE. | 11.41 | 0 | 0 | 100
Total | [13 empty] | 432.85 | 0 | 0