## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 3687/BD | 14/12/2022 | 14/12/2022 | Resource Division | 7.03 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 3710/BD | 15/12/2022 | 15/12/2022 | Resource Division | 18.47 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Ghatpatila (Zone-I) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002929/2021-2022 | 539/Bon | 03/11/2021 | 24/11/2021 | ROY CHOWDHURY CONSTRUCTION. | 2.52 | 2.49 | 98.83 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ghatpatila Zone-I Water Supply Scheme in Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 3469/BD | 01/12/2022 | 01/03/2023 | H.I.ENTERPRISE. | 471.66 | 413.3 | 87.63 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (Head Work Site) under Bongaon Sub-Division P.H.E.Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1548/BD | 22/05/2023 | 21/06/2023 | SAHA CONSTRUCTION & CO | 16.16 | 13.69 | 84.7 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Acceptance cum work order forSinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte.-- Part- B | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 1547/BD | 22/05/2023 | 21/06/2023 | SAHA CONSTRUCTION & CO | 16.17 | 13.75 | 85.02 | 100
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Supply fitting fixing of change over switch at P.H.No-I & II ,Zone-I of Ghatpatila and P.H.No- I & II of Kola W/S Scheme under EMSD-I, P.H.E. Dte. Dist.-24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/001819/2023-2024 | 1814/EMSD-I | 18/08/2023 | 02/09/2023 | SUNRISE ENGINEERING CORPORATION | 0.86 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 1255/BD | 25/04/2023 | 25/04/2023 | Resource Division | 73.62 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001487/2023-2024 | 4464/BD | 21/11/2023 | 14/12/2023 | KAMAL HALDER. | 6.86 | 3.43 | 50.09 | 60
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001454/2023-2024 | 4408/BD | 10/11/2023 | 09/01/2024 | ONKAR ENTERPRISE. | 11.79 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Ghatpatila Zone-I WS Scheme |  |  | BILL/00832/2024-2025 | BP-02024-25-262 | 12/09/2024 | 12/09/2024 | H.I.ENTERPRISE. | 22.17 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and Tube well connection under Augmentation work at Ghatpatila W/S Scheme (Zone - I), Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2024-2025 | 1770/BD | 01/07/2024 | 12/05/2025 | ROY CHOWDHURY CONSTRUCTION. | 22.88 | 7.37 | 32.21 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Repairing of outdoor light & allied work at P.H. no.l , Zone -I of Ghatpatila WS Scheme under EMSD-l, P.H.E. Dte. Dist.-24Pgs(N). | Assistant Engineer | Junior Engineer | ORD/000013/2025-2026 | 450/EMSD-I | 08/04/2025 | 01/07/2025 | GHOSH AND GHOSH | 2.66 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ghatpatila (Zone-I) to accommodate FHTC | SM/11540 | Augmentation | Quotation for 10 KWp Solar power plant at P.H.No- I , Zone - I of Ghatpatila ground water based water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/03029/2025-2026 |  | 07/01/2026 | 07/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 673 | 454.03 | 67.46