## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GACHHARATI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002783/2021-2022 | 199/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.69 | 2.63 | 97.74 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 3812/BD | 23/12/2022 | 23/12/2022 | Resource Division | 0.33 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | Augmentation | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Gachharati water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2022-2023 | 2934/BD | 26/09/2022 | 25/12/2022 | SANJOY BAKSHI | 140.52 | 53.21 | 37.86 | 46
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | Augmentation | Acceptance cum work order for Sinking of 1nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method at Pump House No.-1 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Gachharati Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001152/2022-2023 | 675/BD | 01/03/2023 | 31/03/2023 | DHELA BABA ENTERPRISE | 19.62 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gachharati to accommodate FHTC | SM/11541 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/000026/2024-2025 | 1483/EMD | 03/06/2024 | 28/03/2025 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 25
Total | [13 empty] | 215.33 | 55.84 | 25.93