## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Jafarpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000770/2024-2025 | 3256/BD | 25/11/2024 | 25/12/2024 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Jafarpur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000865/2022-2023 | 3763/BD | 20/12/2022 | 20/03/2023 | H.I.ENTERPRISE. | 438.55 | 438.38 | 99.96 | 82
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Relaying of 90mm, 110mm, 125mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 429/465 & 543 to 563 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 1023/BHTSD | 28/06/2024 | 05/07/2024 | RAKESH ENTERPRISE. | 0.99 | 0 | 0 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Relaying of 90mm, 110mm dia UPVC pipe line and repairing of FHTC connection which damaged due to construction of drain from local Panchayet at Node no. 103 to 137 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000249/2024-2025 | 1022/BHTSD | 28/06/2024 | 05/07/2024 | RAKESH ENTERPRISE. | 0.89 | 0 | 0 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Repairing of damaged concrete road due to laying of Pipe Line in various place of zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. [SM/11585] | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 916/BHTSD | 24/05/2024 | 31/05/2024 | RAKESH ENTERPRISE. | 0.96 | 0 | 0 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Relaying of 160mm dia UPVC pipe line and repairing of FHTC connection which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000252/2024-2025 | 1025/BHTSD | 28/06/2024 | 05/07/2024 | RAKESH ENTERPRISE. | 0.96 | 0 | 0 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Relaying of 75mm, 90mm, 110mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 402 to 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000251/2024-2025 | 1024/BHTSD | 28/06/2024 | 05/07/2024 | RAKESH ENTERPRISE. | 0.99 | 0 | 0 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Jafarpur to accommodate FHTC | SM/11585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 489/BD | 17/02/2023 |  | Resource Division | 28.3 | 0 | 0 | 0
Total | [13 empty] | 21833.15 | 438.38 | 2.01