## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 2308/BD | 03/08/2022 | 03/08/2022 | Resource Division | 2.43 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 4418/BD | 10/11/2023 | 10/11/2023 | Resource Division | 6.16 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Champapukuria Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000772/2024-2025 | 3261/BD | 25/11/2024 | 25/12/2024 | NEW MA TARA ENTERPRISE. | 21.59 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Champapukuria water supply scheme in Basirhat-II block of North 24 Parganas Distruct under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000776/2022-2023 | 3473/BD | 01/12/2022 | 01/03/2023 | UTPAL CONSTRUCTION & CO. | 211.02 | 210.11 | 99.57 | 92
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Acceptance cum work order for special repair and renovation of existing structures like Pump House, boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Champapukur, Chandipur, Dakhin Debipur, Dhopaberia, Srinagar and Sangrampur Water Supply Scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000286/2025-2026 | 2424/BD | 14/07/2025 | 11/12/2025 | DAS ENTERPRISE | 82.86 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Champapukuria to accommodate FHTC | SM/11586 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21663.82 | 210.11 | 0.97