## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | supply delivery & installation of automatic programmable logic control system at P.h.IIat P.h no. II under Kachua-Swarupnagar w/s scheme. 24Pgs(N) |  |  | ORD/000494/2021-2022 | 605/EMSD I | 11/03/2022 | 18/03/2022 | ESENCE ENGINEERING CONCERN | 2.76 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 3817/BD | 23/12/2022 | 23/12/2022 | Resource Division | 87.92 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Payment of Earnest Money for New Service Connection at Water Treatment Plant at Basirhat Swarupnagar |  |  | VCH/003299/2022-2023 |  | 07/11/2022 | 07/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2022-2023 | 607/BD | 23/02/2023 | 23/02/2023 | Resource Division | 8.6 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 4422/BD | 10/11/2023 | 10/11/2023 | Resource Division | 9.24 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kachua Swarupnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000790/2022-2023 | 3548/BD | 06/12/2022 | 06/03/2023 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 395.76 | 390.22 | 98.6 | 65
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 15.66 | 0.07 | 11
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kachua Swarupnagar to accommodate FHTC | SM/11591 | Augmentation | Acceptance cum work order for Restoration of Concrete roads and emergency protection work under different places of Kachua Swarupnagar Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/000403/2025-2026 | 2673/BD | 30/07/2025 | 29/08/2025 | ALAM ENTERPRISE | 7.99 | 0 | 0 | 0
Total | [13 empty] | 21852.23 | 405.88 | 1.86