## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chowberia Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002788/2021-2022 | 127/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.43 | 99.53 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 3689/BD | 14/12/2022 | 14/12/2022 | Resource Division | 124.58 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 3662/BD | 13/12/2022 | 13/12/2022 | Resource Division | 14 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chowberia Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000788/2022-2023 | 3546/BD | 06/12/2022 | 06/03/2023 | M/S B.K.ENTERPRISE. | 279.32 | 227.89 | 81.59 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chowberia water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/003000/2021-2022 | 532/Bon | 03/11/2021 | 24/11/2021 | A.D.ENTERPRISE. | 2.52 | 2.51 | 99.48 | 1
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep) under Krishnachandrapur W/S Scheme and Chowberia W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001173/2023-2024 | 4801/EMD | 09/08/2023 | 01/01/2025 | A.G ENTERPRISE. | 52.15 | 24.25 | 46.51 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000795/2023-2024 | 2695/BD | 04/09/2023 | 04/10/2023 | DHELA BABA ENTERPRISE | 16.17 | 11.74 | 72.63 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001110/2023-2024 | 2923/BD | 26/09/2023 | 26/10/2023 | SAHA CONSTRUCTION & CO | 16.14 | 13.72 | 85.02 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Acceptance cum work order for Construction of Boundary wall aand Construction of Approach Road at 1st T/W site under Augmentation of Chauberia water Supply scheme, Bongaon Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001499/2023-2024 | 4485/BD | 23/11/2023 | 16/12/2023 | TAPAN GHOSH. | 5.58 | 5.57 | 99.82 | 100
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Quotation for New service connection at OHR site of Chowberia water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) |  |  | BILL/02265/2024-2025 | BP-181 | 13/12/2024 | 13/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chauberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001564/2023-2024 | 53/BD | 05/01/2024 | 28/02/2025 | TAPAN GHOSH. | 6.03 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chowberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 2418/BD | 23/08/2024 | 17/10/2025 | M/S B.K.ENTERPRISE. | 35.07 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC | SM/11592 | Augmentation | Restoration Charges for Road damages for pipe laying of "Gopalnagar Chowberia Ukhra Road" |  |  | BILL/01312/2025-2026 |  | 28/08/2025 | 28/08/2025 | EXECUTIVE ENGINEER, PWD HIGHWAY DIVISION NO II | 12.21 | 0 | 0 | 0
Total | [13 empty] | 572.68 | 289.12 | 50.49