## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-I) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002770/2021-2022 | 123/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.45 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayageria Zone-I water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002949/2021-2022 | 533/BD | 03/11/2021 | 24/11/2021 | DURGA ENTERPRISE. | 2.52 | 2.48 | 98.66 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 3655/BD | 13/12/2022 | 13/12/2022 | Resource Division | 20.38 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2022-2023 | 3688/BD | 14/12/2022 | 14/12/2022 | Resource Division | 35.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000824/2022-2023 | 3604/BD | 09/12/2022 | 09/03/2023 | MONDAL ENTERPRISE. (BARASAT) | 462.8 | 461.39 | 99.7 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhayagharia Water Supply Scheme (Z-I), Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000347/2024-2025 | 2420/BD | 23/08/2024 | 22/10/2024 | ACHINTA KUMAR HALDER. | 28.75 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhaighoria (Zone-I) water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000794/2023-2024 | 2683/BD | 04/09/2023 | 04/10/2023 | DHELA BABA ENTERPRISE | 16.17 | 14.45 | 89.33 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-I) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. |  |  | ORD/000082/2025-2026 | 533/Bon | 22/04/2025 | 29/04/2025 | ELDORADO | 0.55 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Bongaon S.D. Hospital w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. |  |  | ORD/000081/2025-2026 | 532/Bon | 22/04/2025 | 29/04/2025 | ELDORADO | 0.55 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhayageria (Zone-I) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 2691/BD | 04/09/2023 | 25/02/2025 | JOY HIND TUBEWELLS. | 16.16 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001743/2023-2024 | 559/BD | 22/02/2024 | 01/07/2025 | KAMAL HALDER. | 7.2 | 3.15 | 43.69 | 60
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC | SM/11593 | Augmentation | Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Chhaygharia (Zone-I) W/S Scheme under Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001460/2024-2025 | 1504/Bon | 30/12/2024 | 29/05/2025 | IMPULSE INTERNATIONAL | 4.79 | 0 | 0 | 100
Total | [13 empty] | 598.97 | 484.91 | 80.96