## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chhaygharia (Zone-III) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002927/2021-2022 | 535/Bon | 03/11/2021 | 24/11/2021 | VAI ENTERPIRSE. | 2.52 | 2.47 | 98.09 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia (Zone-III) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 3491/BD | 02/12/2022 | 02/03/2023 | M/S PROGATI ENTERPRISE. | 296.33 | 296.19 | 99.95 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-III) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002787/2021-2022 | 125/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.42 | 3.4 | 99.44 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 3653/BD | 13/12/2022 | 13/12/2022 | Resource Division | 15.03 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 3695/BD | 14/12/2022 | 14/12/2022 | Resource Division | 110.28 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-III) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1546/BD | 22/05/2023 | 21/06/2023 | NEW MA TARA ENTERPRISE. | 15.81 | 10.08 | 63.73 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2024-2025 | 2419/BD | 23/08/2024 | 19/06/2025 | ONKAR ENTERPRISE. | 42.48 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001745/2023-2024 | 561/BD | 22/02/2024 | 07/04/2024 | ROY ENGINEERS. | 10.23 | 9.86 | 96.4 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-III under Chhaygharia ground water based water supply scheme under Block_ Bongaon Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002818/2023-2024 | 806/EMD | 11/03/2024 | 01/03/2025 | INDIA ENTERPRISE | 25.79 | 14.56 | 56.46 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Laying of UPVC pipe line at different damaged portions under Augmentation work at Chhaygharia (Zone-III) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2024-2025 | 1384/Bon | 26/11/2024 | 20/02/2025 | JOY GURU ENTERPRISE | 4.96 | 1.31 | 26.47 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Chhaygharia (Zone-III) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/000849/2024-2025 | 3385/BD | 03/12/2024 | 02/05/2025 | VAI ENTERPRISE. | 12.02 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-III) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. |  |  | ORD/000084/2025-2026 | 539/Bon | 23/04/2025 | 30/04/2025 | ELDORADO | 0.55 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order for Restoration of damaged pipe line due to Construction of Pucca Drain by laying of UPVC pipe at different places under Chhaigharia Gram Panchayet, Bongaon Block of Chhaigharia (Zone - III) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 2053/BD | 20/06/2025 | 17/03/2026 | VAI ENTERPRISE. | 23.12 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Acceptance cum work order Providing Functional Household Tap Connection (FHTC) to the uncovered household at Jayantipur mouza including laying of UPVC pipe and allied works under Augmentation work at Chhaigharia (Zone-III) W/S Scheme under Chhaigharia G.P., Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000021/2025-2026 | 1649/BD | 21/05/2025 | 19/08/2025 | SUJAN KUMAR MISTRY | 25.23 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC | SM/11594 | Augmentation | Quotation for New service connection at P.H.No- OHR ,Zone - III of Chhaygharia water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/02467/2024-2025 | BP-211 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.04 | 0 | 0 | 0
Total | [13 empty] | 592.8 | 337.88 | 57