## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Formal Work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nurpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 2398/BD | 17/08/2022 | 15/11/2022 | M/S NIRMAN CONSTRUCTION. | 183.61 | 179.26 | 97.63 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 2475/BD | 24/08/2022 | 24/08/2022 | Resource Division | 4.91 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Champali W/S Scheme and Nurpur W/S SchemeDistrict of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001673/2022-2023 | 1004/EMD | 09/03/2023 | 08/04/2023 | PADMA ENGINEERING CO. | 53 | 14.37 | 27.11 | 60
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Nurpur water supply scheme, Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001251/2023-2024 | 4181/BD | 30/10/2023 | 29/10/2025 | SARKAR ENTERPRISE & CO. | 122.36 | 55.65 | 45.48 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Restoration of Road to be damaged for laying of pipe line as proposed by Barasat Division, PHED along Bhebia Bazar to Sirishtala Road via Dakshin Bhebia from Chainage 0.00 kmp to 2.25 km under Barasat Highway Divn-I PWRD (Nurpur W/S scheme). |  |  | BILL/00241/2025-2026 |  | 16/05/2025 | 16/05/2025 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 29.72 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2022-2023 | 2438/BD | 22/08/2022 | 11/12/2024 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 22.14 | 49.86 | 100
Total | [13 empty] | 438.02 | 271.42 | 61.97