## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2022-2023 | 2438/BD | 22/08/2022 | 21/09/2022 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 22.14 | 49.86 | 54
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Formal Work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nurpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 2398/BD | 17/08/2022 | 15/11/2022 | M/S NIRMAN CONSTRUCTION. | 183.61 | 179.26 | 97.63 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 2475/BD | 24/08/2022 | 24/08/2022 | Resource Division | 4.91 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC. | SM/11595 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Champali W/S Scheme and Nurpur W/S SchemeDistrict of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001673/2022-2023 | 1004/EMD | 09/03/2023 | 08/04/2023 | PADMA ENGINEERING CO. | 53 | 14.37 | 27.11 | 60
Total | [13 empty] | 285.93 | 215.77 | 75.46