## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001177/2022-2023 | 790/BD | 13/03/2023 | 12/04/2023 | ABDUL ALIM MONDAL. | 21.44 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 1189/BD | 19/04/2023 | 18/07/2023 | S.S.ENTERPRISE. (BAMANGACHI) | 417.27 | 0 | 0 | 88
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 922/BD | 22/03/2023 | 22/03/2023 | Resource Division | 22.12 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001604/2023-2024 | 32-HSD.. | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Emdadul Haque in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000983/2024-2025 | 3461/BD | 09/12/2024 | 08/01/2025 | M/S ANUBHAB CONSTRUCTION. | 8.77 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000740/2023-2024 | 2493/BD | 18/08/2023 | 17/09/2023 | M/S RAJPATH CONSTRUCTION. | 43.9 | 0 | 0 | 80
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 2886/BD | 20/09/2023 | 19/09/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 152.49 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 200 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001601/2023-2024 | 30/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0 | 0 | 80
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 150 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001602/2023-2024 | 31/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0 | 0 | 82
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Ph No- 2 within Malancha W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2024-2025 | 993/HSD | 29/08/2024 | 08/09/2024 | M/S RAJPATH CONSTRUCTION. | 0.87 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001856/2023-2024 | 32/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 0 | 62
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II(Rep.) and III(New) (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Malancha W/S Scheme District of 24 Pgs. (N) NIET NO. 32 OF EE/EMD OF 2022-23 (SL. NO. -15) | Assistant Engineer | Junior Engineer | ORD/001675/2022-2023 | 1013/EMD | 09/03/2023 | 02/06/2025 | MAHADEV ENTERPRISE | 66.24 | 0 | 0 | 40
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000011/2025-2026 | 1606/BD | 19/05/2025 | 18/06/2025 | M/S RAJPATH CONSTRUCTION. | 5.91 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Salauddin Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000036/2025-2026 | 1528/BD | 14/05/2025 | 04/06/2025 | MD.SALIM GAZI. | 10.2 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 2865/BD | 30/09/2024 | 29/12/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 151.25 | 0 | 0 | 100
Total | [13 empty] | 904.17 | 0 | 0