## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II(Rep.) and III(New) (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Malancha W/S Scheme District of 24 Pgs. (N) NIET NO. 32 OF EE/EMD OF 2022-23 (SL. NO. -15) | Assistant Engineer | Junior Engineer | ORD/001675/2022-2023 | 1013/EMD | 09/03/2023 | 02/06/2025 | MAHADEV ENTERPRISE | 66.24 | 34.24 | 51.68 | 40
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 1189/BD | 19/04/2023 | 18/07/2023 | S.S.ENTERPRISE. (BAMANGACHI) | 417.27 | 415.63 | 99.61 | 88
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000740/2023-2024 | 2493/BD | 18/08/2023 | 17/09/2023 | M/S RAJPATH CONSTRUCTION. | 43.9 | 34.01 | 77.48 | 80
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 2886/BD | 20/09/2023 | 19/09/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 152.49 | 141.63 | 92.88 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001177/2022-2023 | 790/BD | 13/03/2023 | 12/04/2023 | ABDUL ALIM MONDAL. | 21.44 | 17.49 | 81.57 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000261/2022-2023 | 922/BD | 22/03/2023 | 22/03/2023 | Resource Division | 22.12 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001604/2023-2024 | 32-HSD.. | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Emdadul Haque in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000983/2024-2025 | 3461/BD | 09/12/2024 | 08/01/2025 | M/S ANUBHAB CONSTRUCTION. | 8.77 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 150 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001602/2023-2024 | 31/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0.95 | 100.53 | 82
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 200 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001601/2023-2024 | 30/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0.95 | 100.49 | 80
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/001856/2023-2024 | 32/HSD | 09/01/2024 | 19/01/2024 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0.92 | 100.47 | 62
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 2865/BD | 30/09/2024 | 29/12/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 151.25 | 71.11 | 47.01 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Ph No- 2 within Malancha W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2024-2025 | 993/HSD | 29/08/2024 | 08/09/2024 | M/S RAJPATH CONSTRUCTION. | 0.87 | 0 | 0 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Ajibar Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000984/2024-2025 | 3460/BD | 09/12/2024 | 08/05/2025 | BARNALI DUTTA | 9.41 | 0 | 0 | 100
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000011/2025-2026 | 1606/BD | 19/05/2025 | 18/06/2025 | M/S RAJPATH CONSTRUCTION. | 5.91 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Salauddin Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000036/2025-2026 | 1528/BD | 14/05/2025 | 04/06/2025 | MD.SALIM GAZI. | 10.2 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2025-2026 | 1632/BD | 20/05/2025 | 04/06/2025 | NEW MANGES INDUSTRIAL CORPORATION | 11.78 | 0 | 0 | 100
18 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Laying of UPVC distribution pipe line for damaged portion due to construction of SRDA road from shop of Saidul Molla to N/H/O Monirul Molla and other allied works in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001428/2024-2025 | 407/BD | 06/02/2025 | 08/03/2025 | S.S.ENTERPRISE. (BAMANGACHI) | 14.19 | 3.76 | 26.48 | 100
19 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC. | SM/11596 | Augmentation | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001608/2024-2025 | 472/HSD | 28/02/2025 | 10/03/2025 | M/S RAJPATH CONSTRUCTION. | 0.75 | 0 | 0 | 100
Total | [13 empty] | 940.3 | 720.67 | 76.64