## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002933/2021-2022 | 528/BON | 01/11/2021 | 22/11/2021 | A.D.ENTERPRISE. | 2.52 | 2.48 | 98.2 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000113/2022-2023 | 3697/BD | 14/12/2022 | 14/12/2022 | Resource Division | 21.19 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ashudi Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2022-2023 | 3550/BD | 06/12/2022 | 06/03/2023 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 156.77 | 99.89 | 63.71 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Laying of badly damaged distribution pipe line with bamboo pile beside road and other allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000748/2023-2024 | 603/Bon | 04/08/2023 | 19/08/2023 | ROY CHOWDHURY CONSTRUCTION. | 1.62 | 1.61 | 99.43 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ashudi Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001148/2023-2024 | 2943/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 14.83 | 92.03 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site and 2nd Pump House site under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001749/2023-2024 | 571/BD | 22/02/2024 | 07/04/2024 | BHABANI ENTERPRISE. | 10.39 | 10.11 | 97.24 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001782/2023-2024 | 626/BD | 28/02/2024 | 13/04/2024 | R.K.MANDAL & CO. | 22.68 | 22.16 | 97.72 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1538/BD | 07/06/2024 | 22/07/2024 | A. R CONS | 12.57 | 12.54 | 99.8 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II Matiagacha (Block-Habra II) W/S Scheme and Pump House No.I & II Ashudi W/S scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001915/2023-2024 | 6738/EMD | 29/11/2023 | 01/06/2025 | M/S S.R. ENTERPRISE | 42.55 | 0 | 0 | 50
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ashudi to accommodate FHTC | SM/11597 | Augmentation | Acceptance cum work order for Additional laying of pipe line with UPVC pipe due to damage of existing pipe line and allied works and construction of IEP back wash drain and allied works under Augmentation work at Ashudi W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2025-2026 | 1524/BD | 14/05/2025 | 10/11/2025 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 33.14 | 0 | 0 | 80
Total | [13 empty] | 319.54 | 163.62 | 51.2