## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001348/2021-2022 | 144/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block withinthe Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002899/2021-2022 | 144/ BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Work order for repairing & renovation of Pump House and allied works of Simulpur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002943/2021-2022 | 587/ BON | 15/12/2021 | 05/01/2022 | ONKAR ENTERPRISE. | 2.52 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Shimulur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002972/2021-2022 | 631/ BON | 31/12/2021 | 15/01/2022 | ONKAR ENTERPRISE. | 1.26 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 3690/BD | 14/12/2022 | 14/12/2022 | Resource Division | 52.1 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 3654/BD | 13/12/2022 | 13/12/2022 | Resource Division | 40.85 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000797/2023-2024 | 2697/BD | 04/09/2023 | 04/10/2023 | NADIA TUBEWELLS | 16.16 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 4798/EMD | 09/08/2023 | 08/09/2023 | ORIENTAL ENGINEERING CO. | 91.05 | 0 | 0 | 80
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur Water Supply Scheme (2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001113/2023-2024 | 2936/BD | 27/09/2023 | 12/12/2024 | JOY GURU ENTERPRISE | 16.12 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site, 2nd Pump House Site & 3rd Pump House Site under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001747/2023-2024 | 564/BD | 22/02/2024 | 07/04/2024 | M/S SUKANTA ENTERPRISE. | 12.72 | 0 | 0 | 100
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Formal work order for Additional laying of UPVC pipe with allied works to connect every house hold connection under Augmentation work at Simulpur W/S Scheme Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001767/2023-2024 | 610/BD | 27/02/2024 | 27/05/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 102.67 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001784/2023-2024 | 628/BD | 28/02/2024 | 13/04/2024 | TAPAN GHOSH. | 6.03 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Construction of Latrine at Head Work site for Augmentation of Shimulpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/000616/2025-2026 | 672/Bon | 26/05/2025 | 10/07/2025 | A.D.ENTERPRISE. | 1.75 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Shimulpur to accommodate FHTC | SM/11598 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection(FHTC) for Augmentation of Shimulpur water supply scheme under Bongaon Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 1126/BD | 11/04/2023 | 31/03/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 639.23 | 0 | 0 | 100
Total | [13 empty] | 991.14 | 0 | 0