## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Gobindapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002971/2021-2022 | 585/ BON | 15/12/2021 | 05/01/2022 | M/S SAYAN ENTERPRISE. | 2.52 | 2.31 | 91.54 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3488/BD | 02/12/2022 | 02/03/2023 | M/S NIRMAN CONSTRUCTION. | 341.88 | 296.38 | 86.69 | 99
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 170/BD | 19/01/2023 | 26/05/2025 | KINGS & CO. | 437.87 | 190.66 | 43.54 | 66
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as to convert the mouzas into Swajal Gram including laying of UPVC pipe, Pump Connection of 1 no. newly sunk Replacement Tube well with rising main by DI pipe and allied works under Augmentation of Gobindapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2025-2026 | 1384/BD | 30/04/2025 | 29/06/2025 | M/S SAYAN ENTERPRISE. | 11.5 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Acceptance cum work order for Repair and renovation works of 350cum capacity 20mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Gobindapur Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2024-2025 | 3403/BD | 04/12/2024 | 04/03/2025 | UPWARDS ENGINEERING PRIVATE LIMITED. | 8.62 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Puturia W/S Scheme, Bahira W/S Scheme, Gabberia W/S Scheme and Gobindapur (Block-Bagdah) W/S Scheme, District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001174/2023-2024 | 4802/EMD | 09/08/2023 | 08/09/2023 | M/S. SAJAHAN CHOWDHURY | 88.56 | 10.17 | 11.49 | 70
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gobindapur & Adjoing Mouza to accommodate FHTC | SM/11599 | Augmentation | Quotation for 10 KWp Solar power plant at P.H.No- I of Gobindapur ground water based water supply scheme under EMSD-I ,PHE Dte. in Dist.- 24Pgs(N). |  |  | BILL/03028/2025-2026 |  | 07/01/2026 | 07/01/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 891.11 | 499.52 | 56.06