## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Koniara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002969/2021-2022 | 552/ BON | 03/11/2021 | 24/11/2021 | K. ENTERPRISE | 2.52 | 2.49 | 98.6 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Koniara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001338/2021-2022 | 137/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 3656/BD | 13/12/2022 | 13/12/2022 | Resource Division | 12.62 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 3693/BD | 14/12/2022 | 14/12/2022 | Resource Division | 30.39 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.22 to 28.02.23=181 days. | Assistant Engineer |  | ORD/000949/2022-2023 | 1484/HSD | 29/08/2022 | 28/02/2023 | SUSMITA MANDAL. | 2.7 | 9.29 | 344.44 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kaniara Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3764/BD | 20/12/2022 | 20/03/2023 | SUPER SKILL. | 341.46 | 338.45 | 99.12 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 2689/BD | 04/09/2023 | 04/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.83 | 85.82 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 2687/BD | 04/09/2023 | 04/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.64 | 84.6 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Renovation of 32 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Koniara water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001543/2023-2024 | 14/BD | 02/01/2024 | 02/03/2024 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 36.22 | 28.24 | 77.98 | 100
10 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Kaniara W/S Scheme, Kamalabas W/S Scheme and Hariharpur W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 4800/EMD | 09/08/2023 | 01/01/2025 | H.K. DAS & CO. | 66.46 | 30.48 | 45.85 | 90
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000024/2025-2026 | 1385/BD | 30/04/2025 | 29/06/2025 | UPWARDS ENGINEERING PRIVATE LIMITED. | 11.42 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer |  | ORD/000467/2025-2026 | 2860/BD | 14/08/2025 | 28/09/2025 | HAQUE ENTERPRISE | 6.12 | 0 | 0 | 0
Total | [13 empty] | 545.88 | 440.14 | 80.63