## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Koniara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002969/2021-2022 | 552/ BON | 03/11/2021 | 24/11/2021 | K. ENTERPRISE | 2.52 | 2.49 | 98.6 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Koniara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001338/2021-2022 | 137/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 3656/BD | 13/12/2022 | 13/12/2022 | Resource Division | 12.62 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 3693/BD | 14/12/2022 | 14/12/2022 | Resource Division | 30.39 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.22 to 28.02.23=181 days. | Assistant Engineer |  | ORD/000949/2022-2023 | 1484/HSD | 29/08/2022 | 28/02/2023 | SUSMITA MANDAL. | 2.7 | 9.29 | 344.44 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kaniara Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3764/BD | 20/12/2022 | 20/03/2023 | SUPER SKILL. | 341.46 | 338.45 | 99.12 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 2689/BD | 04/09/2023 | 04/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.83 | 85.82 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 2687/BD | 04/09/2023 | 04/10/2023 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 13.64 | 84.6 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Renovation of 32 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Koniara water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001543/2023-2024 | 14/BD | 02/01/2024 | 02/03/2024 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 36.22 | 28.24 | 77.98 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000024/2025-2026 | 1385/BD | 30/04/2025 | 29/06/2025 | UPWARDS ENGINEERING PRIVATE LIMITED. | 11.42 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer |  | ORD/000467/2025-2026 | 2860/BD | 14/08/2025 | 28/09/2025 | HAQUE ENTERPRISE | 6.12 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram with laying of UPVC pipe line and Repairing and Renovation of AIRP Compressor Room under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000972/2024-2025 | 1403/Bon | 28/11/2024 | 28/03/2025 | HAQUE ENTERPRISE | 4.83 | 0 | 0 | 100
13 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kaniara to accommodate FHTC | SM/11600 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Kaniara W/S Scheme, Kamalabas W/S Scheme and Hariharpur W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 4800/EMD | 09/08/2023 | 01/01/2025 | H.K. DAS & CO. | 66.46 | 30.48 | 45.85 | 90
Total | [13 empty] | 550.71 | 440.14 | 79.92