## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Hariharpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002973/2021-2022 | 521/ BON | 28/10/2021 | 18/11/2021 | ANKIT CONSTRUCTION | 2.51 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 1256/BD | 25/04/2023 | 25/04/2023 | Resource Division | 12.08 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Hariharpur Water Supply Scheme (H/W Site)within the jurisdiction of BongaonSub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001116/2023-2024 | 2939/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.11 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Approach Road at 2nd Tube Well site and Construction of Boundary wall and Approach Road at Head Work and 2nd T/W site under Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001781/2023-2024 | 625/BD | 28/02/2024 | 13/04/2024 | JEET ENTERPRISE. | 7.66 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Acceptance cum work order for Renovation of 35 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Hariharpur Water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001765/2023-2024 | 511/BD | 20/02/2024 | 20/04/2024 | DEBAPRASAD MONDAL. | 38.43 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001791/2023-2024 | 648/BD | 29/02/2024 | 30/03/2024 | A.D.ENTERPRISE. | 13.35 | 0 | 0 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001006/2022-2023 | 175/BD | 19/01/2023 | 07/07/2025 | M/S R.K. ENTERPRISE | 173.76 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Hariharpur to accommodate FHTC | SM/11601 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Replacement) under Kaniara W/S Scheme, Kamalabas W/S Scheme and Hariharpur W/S Scheme District of 24 Pgs. (N). | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 4800/EMD | 09/08/2023 | 01/01/2025 | H.K. DAS & CO. | 66.46 | 0 | 0 | 90
Total | [13 empty] | 330.37 | 0 | 0