## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Kamlabas water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002955/2021-2022 | 592/BON | 22/12/2021 | 12/01/2022 | MONDAL & CO.(BON) | 2.52 | 2.31 | 91.49 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 1259/BD | 25/04/2023 |  | Resource Division | 17.95 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kamalabas Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000836/2022-2023 | 3630/BD | 12/12/2022 | 12/03/2023 | BANERJEE CONSTRUCTION. ( BARASAT) | 181.45 | 131.1 | 72.25 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep replacement T/W by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamlabas Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2023-2024 | 2829/BD | 15/09/2023 | 15/10/2023 | SAHA CONSTRUCTION & CO | 16.14 | 6.73 | 41.68 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at Head Work & 2nd T/W site under Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001750/2023-2024 | 558/BD | 22/02/2024 | 07/04/2024 | S.S. INFRASTRUCTURE | 10.36 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | New service connection at P.H.No- II of Kamalabas water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05527/2023-2024 | BP-348-23-24 | 21/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0 | null
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamalabas Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 2944/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 6.65 | 41.26 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Kamlabas w/s scheme Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002274/2023-2024 | 211/Bon | 27/02/2024 | 12/04/2024 | MONDAL & CO.(BON) | 4.39 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001738/2023-2024 | 534/BD | 21/02/2024 | 06/04/2024 | REAL TIME | 12.89 | 6.63 | 51.4 | 100
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Emergent works for repairing pipe line, FHTC refining, ferrule wash with supply of sluice valve and construction of valve chamber under Augmentation work at Kamlabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 490/Bon | 04/04/2024 | 19/04/2024 | MONDAL & CO.(BON) | 4.97 | 2.47 | 49.78 | 100
Total | [13 empty] | 270.7 | 155.88 | 57.58