## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Repairing & Renovation of 02Nos. Pump House and allied works at Kamlabas water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002955/2021-2022 | 592/BON | 22/12/2021 | 12/01/2022 | MONDAL & CO.(BON) | 2.52 | 2.31 | 91.49 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kamalabas Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000836/2022-2023 | 3630/BD | 12/12/2022 | 12/03/2023 | BANERJEE CONSTRUCTION. ( BARASAT) | 181.45 | 131.1 | 72.25 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 1259/BD | 25/04/2023 | 25/04/2023 | Resource Division | 17.95 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamalabas Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 2944/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 13.3 | 82.51 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep replacement T/W by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamlabas Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2023-2024 | 2829/BD | 15/09/2023 | 15/10/2023 | SAHA CONSTRUCTION & CO | 16.14 | 13.46 | 83.36 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001738/2023-2024 | 534/BD | 21/02/2024 | 06/04/2024 | REAL TIME | 12.89 | 13.25 | 102.81 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Kamlabas w/s scheme Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002274/2023-2024 | 211/Bon | 27/02/2024 | 12/04/2024 | MONDAL & CO.(BON) | 4.39 | 4.39 | 99.92 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Emergent works for repairing pipe line, FHTC refining, ferrule wash with supply of sluice valve and construction of valve chamber under Augmentation work at Kamlabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 490/Bon | 04/04/2024 | 19/04/2024 | MONDAL & CO.(BON) | 4.97 | 4.94 | 99.56 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | New service connection at P.H.No- II of Kamalabas water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05527/2023-2024 | BP-348-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Enhancement amount of GST for laying of DI/UPVC distribution pipe line and providing FHTC for Augmentation Kamlanbas wsscheme. |  |  | BILL/01248/2024-2025 | BP-2024-25-416 | 07/10/2024 | 07/10/2024 | BANERJEE CONSTRUCTION. ( BARASAT) | 7.08 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram with laying of UPVC pipe line, Tube Well connection and pipe protection work under Augmentation work at Kamalabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001042/2024-2025 | 3620/BD | 20/12/2024 | 19/05/2025 | MONDAL & CO.(BON) | 10.13 | 0 | 0 | 100
12 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Restoration of existing 140 mm dia UPVC pipe line along the main road by UC Ballah pilling due to soil erosion at the bank of Ichhamati river near Holor Ghat (Chalk Jhitkipota) under Augmentation work of Kamalabas W/S Scheme, Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 1523/BD | 14/05/2025 | 10/11/2025 | ANARUL KHAN. | 61.45 | 0 | 0 | 40
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC | SM/11602 | Augmentation | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kamalabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000156/2025-2026 | 2448/BD | 15/07/2025 | 29/08/2025 | MONDAL ENTERPRISE. (BARASAT) | 23.45 | 0 | 0 | 0
Total | [13 empty] | 362.44 | 182.75 | 50.42