## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Ramnagar Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001350/2021-2022 | 146/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 100 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Repairing & Renovation of 02No. Pump House and allied works at Ramnagar water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002904/2021-2022 | 541/BON | 03/11/2021 | 24/11/2021 | MA CONSTRUCTION. | 2.52 | 2.47 | 98.16 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 3663/BD | 13/12/2022 |  | Resource Division | 7.98 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 3691/BD | 14/12/2022 |  | Resource Division | 12.68 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ramnagar Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000766/2022-2023 | 3472/BD | 01/12/2022 | 01/03/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 200.08 | 199.57 | 99.75 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2023-2024 | 2685/BD | 04/09/2023 | 04/10/2023 | SAHA CONSTRUCTION & CO | 16.17 | 5.87 | 36.28 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 2684/BD | 04/09/2023 | 04/10/2023 | SAHA CONSTRUCTION & CO | 16.17 | 5.61 | 34.69 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Acceptance cum work order for Repairing of Boundary wall at Head Work site, Construction of Boundary wall at 2nd Pump House site and Construction of Approach Road at Head Work site and 2nd T/W Site under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001748/2023-2024 | 565/BD | 22/02/2024 | 07/04/2024 | JP CONSTRUCTION & SUPPLIERS. | 12.84 | 6.33 | 49.28 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001786/2023-2024 | 630/BD | 28/02/2024 | 13/04/2024 | GHOSH CONSTRUCTION | 5.97 | 2.98 | 49.87 | 100
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Ramnagar to accommodate FHTC | SM/11603 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II (Zone-I)(Rep.) and Pump house no-III (New) under Dakshin Bhebia W/S Scheme with Pump House No-I and II under Ramnagar W/S scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001158/2023-2024 | 4808/EMD | 09/08/2023 | 08/09/2023 | A.G ENTERPRISE. | 53.18 | 9.57 | 18 | 40
Total | [13 empty] | 330.57 | 235.37 | 71.2