## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Route Survey, Design Drawing & DPR Preparation for GOKNASREE GOBINDAPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001937/2021-2022 | 193/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.63 | 97.25 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Formal work order for laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Goknashri Gobindapur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001187/2022-2023 | 1042/BD | 31/03/2023 | 08/04/2025 | UTPAL CONSTRUCTION & CO. | 383.12 | 333.4 | 87.02 | 64
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1245/BD | 25/04/2023 | 25/04/2023 | Resource Division | 5.09 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 4412/BD | 10/11/2023 | 10/11/2023 | Resource Division | 16.02 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Goknasree Gobindapur W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity- 60.00 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002029/2023-2024 | 923/BD | 15/03/2024 | 14/05/2024 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 33.01 | 27.58 | 83.54 | 50
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Goknashri Gobindapur to accommodate FHTC | SM/11604 | Augmentation | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer |  | ORD/000287/2025-2026 | 2464/BD | 16/07/2025 | 13/12/2025 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0 | 0
Total | [13 empty] | 522.06 | 364.61 | 69.84