## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Acceptance cum work order for construction of CWR at Sangrampur W/S scheme under Basirhat Sub-Division, P.H.E. Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001165/2021-2022 | 333/BD | 02/02/2022 | 19/03/2022 | MD AMIRUL MOLLA. | 5.2 | 4.49 | 86.5 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Route Survey, Design Drawing & DPR Preparation for SANGRAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002895/2021-2022 | 195/BHT SD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Formal work order for Laying of DI/UPVC distribution system pipeline and Providing FHTC (Functional Household Tap Connection)for augmentation of Sangrampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2022-2023 | 3196/BD | 01/11/2022 | 30/01/2023 | H.I.ENTERPRISE. | 654.07 | 647.44 | 98.99 | 83
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 3811/BD | 23/12/2022 | 23/12/2022 | Resource Division | 83.52 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | New Service Connectio for Sangrampur W/S Scheme |  |  | BILL/00012/2022-2023 | 96/EMD | 29/11/2022 | 29/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | New service connection charge for Sangrampur |  |  | VCH/003340/2022-2023 |  | 14/11/2022 | 14/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.46 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Supply & Installation of Automatically Controlled Diaphragm type Chlorinator at PH-H/L under Sangrampur (AIRP) W/S Scheme under Eastern Mechanical Sub-Division-I, PHE Dte. Dist. 24 Pgs. (N). |  | Junior Engineer | ORD/000041/2023-2024 | 1329/EMSD-I | 31/05/2023 | 20/06/2023 | T.N. BANERJEE | 2.99 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Providing outdoor Illumination arrangement at P.H. - High Lift under Sangrampur W/S Scheme, Dist 24pgs(N). |  | Junior Engineer | ORD/000040/2023-2024 | 1328/EMSD-I | 31/05/2023 | 15/06/2023 | DAS ENTERPRISE (BARANAGAR) | 2.21 | 2.18 | 98.76 | 100
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1101/BD | 06/04/2023 | 06/04/2023 | Resource Division | 92.65 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1659/BD | 05/06/2023 | 05/06/2023 | Resource Division | 10.04 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-II under Sangrampur ground water based water supply scheme under Block_ Basirhat-I Dist. - 24 PARAGANAS (N) under EMD, PHE Dte. (SM/11605) | Assistant Engineer |  | ORD/000654/2024-2025 | 2691/EMD | 20/11/2024 | 20/12/2024 | D.S. ENTERPRISE | 10.54 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Sangrampur WS Scheme |  |  | BILL/00831/2024-2025 | BP-02024-25-262 | 12/09/2024 | 12/09/2024 | H.I.ENTERPRISE. | 34.82 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sangrampur Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. 2nd Call. | Assistant Engineer |  | ORD/001212/2024-2025 | 195/BD | 16/01/2025 | 15/02/2025 | JESMINE ENTERPRISE. | 21.72 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Acceptance cum work order for Construction of Boundary Wall at the Head Work site of Sangrampur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001037/2024-2025 | 59/BD | 07/01/2025 | 05/08/2025 | IKBAL HOSSAIN | 18.27 | 0 | 0 | 40
16 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sangrampur to accommodate FHTC | SM/11605 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/001472/2024-2025 | 147/BHTSD | 29/01/2025 | 18/02/2025 | S.M.TRADERS. | 0.88 | 0 | 0 | 90
Total | [13 empty] | 22288.42 | 658.96 | 2.96