## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Route Survey, Design Drawing & DPR Preparation for PASCHIM MADHYAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002792/2021-2022 | 197/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000198/2022-2023 | 853/BD | 20/03/2023 | 20/03/2023 | Resource Division | 51.49 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2022-2023 | 611/BD | 23/02/2023 | 23/02/2023 | Resource Division | 10.1 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 4426/BD | 10/11/2023 | 10/11/2023 | Resource Division | 13.34 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Paschim Madhyampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001237/2022-2023 | 1040/BD | 31/03/2023 | 02/03/2025 | UTPAL CONSTRUCTION & CO. | 487.91 | 0 | 0 | 68
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Sankchura W/S Scheme and Paschim Madhyampur W/s Scheme District of 24 Pgs. (N) |  |  | ORD/001165/2023-2024 | 4815/EMD | 09/08/2023 | 08/09/2023 | CONCORD ENGINEERING | 79.5 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Paschim Madhyampur to accommodate FHTC | SM/11606 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | Assistant Engineer | Junior Engineer | ORD/001477/2024-2025 | 148/BHTSD | 29/01/2025 | 18/02/2025 | M.R.CONSTRUCTION. | 0.88 | 0 | 0 | 90
Total | [13 empty] | 21987.22 | 0 | 0