## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Formal work order for Laying of DI/UPVC Distribution System pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sankarpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000820/2022-2023 | 3602/BD | 09/12/2022 | 09/03/2023 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 459.43 | 300.52 | 65.41 | 76
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | Assistant Engineer |  | ORD/001036/2024-2025 | 3626/BD | 20/12/2024 | 19/01/2025 | NISHITH BANERJEE | 45.36 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Sankarpur and P/H-II under Debhog W/S Scheme with Pump House No-I under Gachharhati W/S Scheme District of 24 Pgs. (N). | Assistant Engineer |  | ORD/000026/2024-2025 | 1483/EMD | 03/06/2024 | 03/07/2024 | EASTERN INDIA SALES & SERVICE | 52.16 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Acceptance cum work order for Renovation of Iron Elimination Plant at Shankarpur W/S Scheme at Basirhat- I Block under Basirhat Sub division, PHE Dte. Capacity- 93.0625 m3/hr. | Assistant Engineer | Junior Engineer | ORD/002036/2023-2024 | 922/BD | 15/03/2024 | 14/05/2024 | NEER UDYOG | 16.57 | 0 | 0 | 80
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2022-2023 | 490/BD | 17/02/2023 |  | Resource Division | 89.49 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000182/2022-2023 | 604/BD | 23/02/2023 |  | Resource Division | 9.83 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 4420/BD | 10/11/2023 |  | Resource Division | 9.36 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | New Service Connection at PH-II under Shankarpur W/S Scheme. |  |  | BILL/04792/2023-2024 | BP-312-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.52 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | New Service Connection at PH-II under Shankarpur W/S Scheme. |  |  | BILL/04792/2023-2024 | BP-312-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.52 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | New Service Connection at PH-I under Shankarpur W/S Scheme. |  |  | BILL/04793/2023-2024 | BP-311-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
11 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Shankarpur to accommodate FHTC | SM/11607 | Augmentation | New Service Connection at PH-I under Shankarpur W/S Scheme. |  |  | BILL/04793/2023-2024 | BP-311-23-24 | 04/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.84 | 0 | 0 | 0
Total | [13 empty] | 708.91 | 300.52 | 42.39