## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Engagement of 8 personnel (3 nos Sampling Assistant & 5 nos Lab Attendant) in different water testing Laboratories under Barasat Division, PHE Dte.(Amdanga Sub-District Lab, Bagdah Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-District Lab & North 24 Parganas District Lab). [w.e.f. 01.01.2022 to 31.12.2022 i.e. 1(one) year] | Assistant Engineer |  | ORD/001008/2021-2022 | 2684/BD | 31/12/2021 | 31/12/2022 | M/S B.K.ENTERPRISE. | 10.51 | 5.02 | 47.81 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Acceptance cum Work Order for Engagement of 2 personnel (One Chemist/Bacteriologist and one Lab Assistant) in each of 8 nos Laboratories of PHE Department in North 24 Parganas District of West Bengal under Barasat Division, PHE Dte.[w.e.f. 01.10.2021 to 30.09.2022 i.e for 1(one) year] (Amdanga, Bishnupur, Bagdah, Chandpara, Habra, Basirhat, Gokhna, Haroa Sub-District Lab). | Assistant Engineer |  | ORD/002630/2021-2022 | 1959/ BD | 08/10/2021 | 08/10/2022 | FRONTLINE EX-SERVICEMEN BUREAU. | 24.89 | 14.65 | 58.87 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Acceptance cum Work Order for Engagement of Laboratory Personnel (Chemist, Bacteriologist, Laboratory & Sampling Assistants) for District Water Testing Laboratory along with Lab activities under Barasat Division P.H.E. Dte., 24 Pgs(N) for the period 01.01.2022 to 31.12.2022. | Assistant Engineer |  | ORD/000996/2021-2022 | 2683/BD | 31/12/2021 | 12/01/2022 | M/S B.K.ENTERPRISE. | 7.18 | 7.08 | 98.64 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Engagement of the Laboratory Site to Operate Atomic Absorption Spectrophotometer & Laboratory Assistant for a Period of One Year for the office of the Executive Engineer, Barasat Division, PHE Dte. (Period for 01.01.2022 to 31.12.2022= 12 months). Sl.No.02 | Assistant Engineer |  | ORD/003009/2021-2022 | 663/BST | 22/12/2021 | 22/12/2022 | M/S B.K.ENTERPRISE. | 3.74 | 0.45 | 11.99 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Acceptance cum work order for Supply of Chemical & Bacteriological Laboratory personnel for water testing laboratory at A. R. Laboratory cum Inspection Bungalow at Taki, North 24 Parganas under Hasnabad Sub-Division, P.H.E. Dte. For the period 01.01.22 to 30.06.22. | Assistant Engineer |  | ORD/001023/2021-2022 | 2209/HSD | 30/12/2021 | 30/06/2022 | SUNDARBAN ENGINEERS-CO-OPERATIVE-SOCIETY LTD. | 2.51 | 2.51 | 100 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Supply, erection of Sign Board at 10 (Ten) Nos. NABL Recognized Sub District Water Testing Laboratory under Barasat Division, P.H.Engg. Dte. | Assistant Engineer | Junior Engineer | ORD/000986/2022-2023 | 879/BST | 27/12/2022 | 11/01/2023 | PURBA SERVICES | 0.84 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Supply, erection of Sign Board at 1(One) No. NABL Accredited District Water Testing Laboratory and 6 (nos) NABL Recognized Sub District Water Testing Laboratory managed by NGO's under Barasat Division, P.H.Engg. Dte. | Assistant Engineer |  | ORD/000987/2022-2023 | 880/BST | 27/12/2022 | 11/01/2023 | PURBA SERVICES | 0.63 | 0.63 | 100 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Engagement of 3 personnel (1 no. Chemist,1 no.Bacteriologist & 1 nos. Lab Assistant) ) for Hingalganj Sub-District Water Testing Laboratory under Barasat Division,PHE Dte. (w.e.f 01.07.2022 to 31.12.2022 i.e for 6(Six) months). Sl.No.01 | Assistant Engineer | Junior Engineer | ORD/000180/2022-2023 | 467/BST | 09/06/2022 | 09/12/2022 | M/S B.K.ENTERPRISE. | 2.74 | 2.65 | 96.7 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Continuation Work Order for Engagement of 2 personnel (One Chemist/Bacteriologist and one Lab Assistant) in each of 8 nos Laboratories of PHE Department in North 24 Parganas District of West Bengal under Barasat Division, PHE Dte.[w.e.f. 01.10.2022 to 31.12.2022 i.e for 3 (Three) months] (Amdanga, Bishnupur, Bagdah, Chandpara, Habra, Basirhat, Gokhna, Haroa Sub-District Lab). | Assistant Engineer |  | ORD/000671/2022-2023 | 2964/BD | 28/09/2022 | 28/12/2022 | FRONTLINE EX-SERVICEMEN BUREAU. | 6.01 | 5.68 | 94.54 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002744/2022-2023 | BP-2022-23-285 | 23/09/2022 | 23/09/2022 | YOUTH DEVELOPMENT CENTER | 0.14 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003091/2022-2023 | BP-2022-23-399 | 11/11/2022 | 11/11/2022 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002268/2022-2023 | BP-2022-23-165 | 04/08/2022 | 04/08/2022 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002265/2022-2023 | BP-2022-23-159 | 04/08/2022 | 04/08/2022 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00098/2022-2023 | BP-2022-23-477 | 16/12/2022 | 16/12/2022 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003026/2022-2023 | BP-2022-23-361 | 21/10/2022 | 21/10/2022 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002210/2022-2023 | BP-2022-23-201 | 30/08/2022 | 30/08/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002231/2022-2023 | BP-2022-23-198 | 30/08/2022 | 30/08/2022 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002234/2022-2023 | BP-2022-23-203 | 30/08/2022 | 30/08/2022 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002748/2022-2023 | BP-2022-23-283 | 23/09/2022 | 23/09/2022 | PATHER PANCHALI SEVA SAMITY. | 0.14 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002208/2022-2023 | BP-2022-23-202 | 30/08/2022 | 30/08/2022 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003024/2022-2023 | BP-2022-23-363 | 21/10/2022 | 21/10/2022 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00097/2022-2023 | BP-2022-23-479 | 16/12/2022 | 16/12/2022 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002232/2022-2023 | BP-2022-23-199 | 30/08/2022 | 30/08/2022 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002264/2022-2023 | BP-2022-23-160 | 04/08/2022 | 04/08/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002746/2022-2023 | BP-2022-23-287 | 23/09/2022 | 23/09/2022 | BITHARI DISHA. | 0.14 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002266/2022-2023 | BP-2022-23-162 | 04/08/2022 | 04/08/2022 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002267/2022-2023 | BP-2022-23-163 | 04/08/2022 | 04/08/2022 | SARVIK VIVEKANANDA GRAM SEVA SANSTHA. | 0.39 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003090/2022-2023 | BP-2022-23-400 | 11/11/2022 | 11/11/2022 | W.B.C.A.D.C | 0.27 | 0 | 0 | 0
29 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORIUM TO LABORATORY PERSONNEL |  |  | BILL/00094/2022-2023 |  | 12/12/2022 | 12/12/2022 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
30 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00095/2022-2023 | BP-2022-23-480 | 16/12/2022 | 16/12/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
31 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00096/2022-2023 | BP-2022-23-481 | 16/12/2022 | 16/12/2022 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
32 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003022/2022-2023 | BP-2022-23-365 | 21/10/2022 | 21/10/2022 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
33 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002745/2022-2023 | BP-2022-23-286 | 23/09/2022 | 23/09/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.14 | 0 | 0 | 0
34 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002747/2022-2023 | BP-2022-23-288 | 23/09/2022 | 23/09/2022 | W.B.C.A.D.C | 0.1 | 0 | 0 | 0
35 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003095/2022-2023 | BP-2022-23-395 | 11/11/2022 | 11/11/2022 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
36 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003093/2022-2023 | BP-2022-23-397 | 11/11/2022 | 11/11/2022 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
37 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003092/2022-2023 | BP-2022-23-398 | 11/11/2022 | 11/11/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
38 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003094/2022-2023 | BP-2022-23-396 | 11/11/2022 | 11/11/2022 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
39 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002211/2022-2023 | BP-2022-23-200 | 30/08/2022 | 30/08/2022 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
40 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002262/2022-2023 | BP-2022-23-164 | 04/08/2022 | 04/08/2022 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
41 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002263/2022-2023 | BP-2022-23-161 | 04/08/2022 | 04/08/2022 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
42 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003021/2022-2023 | BP-2022-23-366 | 21/10/2022 | 21/10/2022 | W.B.C.A.D.C | 0.27 | 0 | 0 | 0
43 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003025/2022-2023 | BP-2022-23-362 | 21/10/2022 | 21/10/2022 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
44 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/002743/2022-2023 | BP-2022-23-284 | 23/09/2022 | 23/09/2022 | PASCHIMBANGA VIGYAN MANCHA. | 0.14 | 0 | 0 | 0
45 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | VCH/003023/2022-2023 | BP-2022-23-364 | 21/10/2022 | 21/10/2022 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
46 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Acceptance cum work order for Engagement of 16 personnel (2 nos. Chemist, 2 nos. Bacteriologist, 1 no. AAS Operator, 2 nos. Laboratory Assistant,4 nos. Sampling Assistant & 5 nos. Lab Attendent ) in different water testing laboratories under Barasat Division,PHE Dte. (North 24 Pargansa District Lab, Hingalganj Sub-District Lab, Bodai Sub-District Lab., Bagda Sub-District Lab, Chandpara Sub-District Lab, Habra Sub-District Lab, Basirhat Sub-Division Lab ) for 1(one)year (Effect from 01.01.2023 to 31.12.2023.) | Assistant Engineer |  | ORD/001028/2022-2023 | 185/BD | 19/01/2023 | 19/01/2024 | M/S B.K.ENTERPRISE. | 36.04 | 15.46 | 42.9 | 65
47 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Shifting of Hingalganj Sub District Water Testing Laboratory from Hingalganj Block campus to Store Campus of Hingalganj Water Supply Scheme at Sahapur, Village & PO. Hingalganj, North 24 Parganas to make it usable as water testing laboratory Under Barasat Division, P.H. Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/001164/2022-2023 | 132/BST | 28/02/2023 | 07/03/2023 | M/S R.B.S.ENTERPRISE. | 0.95 | 0.95 | 100 | 0
48 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00335/2022-2023 |  | 10/01/2023 | 10/01/2023 | YOUTH DEVELOPMENT CENTER | 0.39 | 0 | 0 | 0
49 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00333/2022-2023 |  | 10/01/2023 | 10/01/2023 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
50 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00485/2022-2023 | BP-2022-23-625 | 27/02/2023 | 27/02/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
51 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00617/2022-2023 |  | 13/03/2023 | 13/03/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
52 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00621/2022-2023 |  | 13/03/2023 | 13/03/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
53 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00237/2023-2024 | BP-2023-24-112 | 01/06/2023 | 01/06/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
54 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00054/2023-2024 | BP-2023-24-58 | 12/05/2023 | 12/05/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
55 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION |  |  | BILL/00455/2023-2024 | BP-2023-24-148 | 26/06/2023 | 26/06/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
56 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JULY'2023. |  |  | BILL/00764/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
57 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00336/2022-2023 | BP-2022-23-547 | 18/01/2023 | 18/01/2023 | BITHARI DISHA. | 0.39 | 0 | 0 | 0
58 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & Lab maintenance. |  |  | BILL/00624/2022-2023 | BP-2022-23-667 | 16/03/2023 | 16/03/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
59 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00567/2023-2024 | BP-2023-24-197 | 11/07/2023 | 11/07/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.45 | 0 | 0 | 0
60 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION |  |  | BILL/00457/2023-2024 | BP-2023-24-146 | 26/06/2023 | 26/06/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
61 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00519/2023-2024 |  | 22/06/2023 | 22/06/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
62 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00337/2022-2023 | BP-2022-23-546 | 18/01/2023 | 18/01/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
63 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00486/2022-2023 | BP-2022-23-626 | 24/02/2023 | 24/02/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
64 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00488/2022-2023 | BP-2022-23-624 | 27/02/2023 | 27/02/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
65 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00619/2022-2023 |  | 13/03/2023 | 13/03/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
66 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed laboratory personnel & Lab maintenance. |  |  | BILL/00626/2022-2023 | BP-2022-23-669 | 16/03/2023 | 16/03/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
67 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. |  |  | BILL/00627/2022-2023 | BP-2022-23-666 | 16/03/2023 | 16/03/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
68 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00239/2023-2024 | BP-2023-24-107 | 01/06/2023 | 01/06/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
69 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00243/2023-2024 | BP-2023-24-108 | 01/06/2023 | 01/06/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
70 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00052/2023-2024 | BP-2023-24-56 | 12/05/2023 | 12/05/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
71 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00053/2023-2024 | BP-2023-24-59 | 12/05/2023 | 12/05/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
72 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00520/2023-2024 |  | 22/06/2023 | 22/06/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
73 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00334/2022-2023 | BP-2022-23-543 | 18/01/2023 | 18/01/2023 | PATHER PANCHALI SEVA SAMITY. | 0.39 | 0 | 0 | 0
74 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00487/2022-2023 | BP-2022-23-622 | 27/02/2023 | 27/02/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
75 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. |  |  | BILL/00625/2022-2023 | BP-2022-23-688 | 16/03/2023 | 16/03/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.51 | 0 | 0 | 0
76 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. |  |  | BILL/00628/2022-2023 | BP-2022-23-670 | 16/03/2023 | 16/03/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
77 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00242/2023-2024 | BP-2023-24-110 | 01/06/2023 | 01/06/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.35 | 0 | 0 | 0
78 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00566/2023-2024 | BP-2023-24-192 | 11/07/2023 | 11/07/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
79 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00569/2023-2024 | BP-2023-24-195 | 11/07/2023 | 11/07/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
80 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00521/2023-2024 |  | 22/06/2023 | 22/06/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
81 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JULY'2023. |  |  | BILL/00763/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
82 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JULY'2023. |  |  | BILL/00761/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
83 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00762/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
84 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00338/2022-2023 | BP-2022-23-544 | 18/01/2023 | 18/01/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.39 | 0 | 0 | 0
85 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00490/2022-2023 | BP-2022-23-623 | 27/02/2023 | 27/02/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
86 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO Lab personnel & lab maintenance. |  |  | BILL/00489/2022-2023 | BP-2022-23-621 | 27/02/2023 | 27/02/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
87 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | VCH/003295/2022-2023 |  | 18/01/2023 | 18/01/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
88 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00618/2022-2023 |  | 13/03/2023 | 13/03/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
89 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00088/2022-2023 | BP-2022-23-548 | 18/01/2023 | 18/01/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
90 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of NGO managed Laboratory Personnel & lab maintenance. |  |  | BILL/00623/2022-2023 | BP-2022-23-665 | 16/03/2023 | 16/03/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
91 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00241/2023-2024 | BP-2023-24-109 | 01/06/2023 | 01/06/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
92 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00055/2023-2024 | BP-2023-24-60 | 12/05/2023 | 12/05/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
93 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION |  |  | BILL/00456/2023-2024 | BP-2023-24-149 | 26/06/2023 | 26/06/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
94 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00568/2023-2024 | BP-2023-24-193 | 11/07/2023 | 11/07/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
95 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00571/2023-2024 | BP-2022-23-196 | 11/07/2023 | 11/07/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
96 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION |  |  | BILL/00454/2023-2024 | BP-2023-24-151 | 26/06/2023 | 26/06/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
97 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JULY'2023. |  |  | BILL/00765/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | FOSET BARRACKPORE SUB-CENTRE. | 0.39 | 0 | 0 | 0
98 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | HONORARIUM FOR LABORATORY PERSONNEL |  |  | BILL/00339/2022-2023 | BP-2022-23-548 | 18/01/2023 | 18/01/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.27 | 0 | 0 | 0
99 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00620/2022-2023 |  | 13/03/2023 | 13/03/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
100 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP |  |  |  | BILL/00616/2022-2023 |  | 13/03/2023 | 13/03/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
101 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JUNE'2023. |  |  | BILL/00570/2023-2024 | BP-2023-24-194 | 11/07/2023 | 11/07/2023 | YOUTH DEVELOPMENT CENTER | 0.51 | 0 | 0 | 0
102 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00522/2023-2024 |  | 22/06/2023 | 22/06/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
103 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00518/2023-2024 | BP-2023-24-150 | 26/06/2023 | 26/06/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
104 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Payment of NGO laboratory for the Month of Nov'2023. |  |  | BILL/02966/2023-2024 | BP-2023-24-618 | 20/12/2023 | 20/12/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
105 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00050/2023-2024 | BP-2023-24-57 | 12/05/2023 | 12/05/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.35 | 0 | 0 | 0
106 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel... |  |  | BILL/00051/2023-2024 | BP-2023-24-61 | 12/05/2023 | 12/05/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.35 | 0 | 0 | 0
107 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF MAY'23 |  |  | BILL/00517/2023-2024 | BP-2023-24-147 | 26/06/2023 | 26/06/2023 | PASCHIMBANGA VIGYAN MANCHA. | 0.51 | 0 | 0 | 0
108 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | Remuneration of Laboratory Personnel.. |  |  | BILL/00240/2023-2024 | BP-2023-24-111 | 01/06/2023 | 01/06/2023 | BITHARI DISHA. | 0.51 | 0 | 0 | 0
109 | NORTH 24 PARGANAS |  | Barasat Division | Yearly operational charges of PHE Dte and NGO managed Laboratories related to WQMSP in connection with Jal Jeevan Mission under Barasat Division PHE Dte. | SM/11625 | Support-WQMSP | REMUNERATION OF LABORATORY PERSONNEL FOR THE MONTH JULY'2023. |  |  | BILL/00760/2023-2024 | BP-2023-24-271 | 17/08/2023 | 17/08/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
Total | [13 empty] | 135.33 | 55.08 | 40.7