## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 3821/BD | 23/12/2022 | 23/12/2022 | Resource Division | 27.91 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 4405/BD | 10/11/2023 | 10/11/2023 | Resource Division | 3.08 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Ghona to accommodate FHTC | SM/11627 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Ghona water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 3184/BD | 01/11/2022 | 30/01/2023 | SHIBU BISWAS. | 179.98 | 130.01 | 72.24 | 85
Total | [13 empty] | 210.97 | 130.01 | 61.62