## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). NIET No. 19 of EE/EMD of 2022-2023 (Sl. No. 19) |  |  | ORD/001903/2023-2024 | 6771/EMD | 29/11/2023 | 29/12/2023 | H.K. DAS & CO. | 13 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 18) |  |  | ORD/000571/2022-2023 | 6392/EMD | 24/11/2022 | 24/12/2022 | DAS ENTERPRISE | 13.02 | 11.34 | 87.14 | 1
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 19) |  |  | ORD/000575/2022-2023 | 6393/EMD | 24/11/2022 | 24/12/2022 | H.K. DAS & CO. | 13 | 11.4 | 87.69 | 0
4 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000066/2023-2024 | 547/CDD | 02/06/2023 | 02/07/2023 | UTTAM KUMAR CHATTERJEE | 21.56 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (TW-II) , Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000083/2023-2024 | 1649/CDD | 17/10/2023 | 16/11/2023 | DEV AND COMPANY | 22.01 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2022-2023 | 493/BD | 17/02/2023 | 17/02/2023 | Resource Division | 10.73 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raghunathpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000746/2022-2023 | 3344/BD | 16/11/2022 | 14/02/2023 | UTPAL CONSTRUCTION & CO. | 180.46 | 155.48 | 86.15 | 88
Total | [13 empty] | 273.77 | 178.22 | 65.1