## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). NIET No. 19 of EE/EMD of 2022-2023 (Sl. No. 19) |  |  | ORD/001903/2023-2024 | 6771/EMD | 29/11/2023 | 29/12/2023 | H.K. DAS & CO. | 13 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 18) |  |  | ORD/000571/2022-2023 | 6392/EMD | 24/11/2022 | 24/12/2022 | DAS ENTERPRISE | 13.02 | 11.34 | 87.14 | 1
3 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Raghunathpur W/S Scheme District of 24 Pgs. (N). (SM/11628) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 19) |  |  | ORD/000575/2022-2023 | 6393/EMD | 24/11/2022 | 24/12/2022 | H.K. DAS & CO. | 13 | 11.4 | 87.69 | 0
4 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (T/W-I) , Basirhat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000066/2023-2024 | 547/CDD | 02/06/2023 | 02/07/2023 | UTTAM KUMAR CHATTERJEE | 21.56 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Raghunathpur W/S Scheme (TW-II) , Barasat-II Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000083/2023-2024 | 1649/CDD | 17/10/2023 | 16/11/2023 | DEV AND COMPANY | 22.01 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Relaying of 75mm dia UPVC Parallel line for repairing of FHTC connections which damaged due to construction of drain from local Panchayet at SriKrishnapur Mouza (Node no. 300 to 307 to 314 to 320) of Raghunathpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000257/2024-2025 | 1028/BHTSD | 28/06/2024 | 05/07/2024 | M/S MAA TARA ENTERPRISE | 0.73 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Relaying of 110mmdia UPVC pipe line damaged due to construction of drain from local Panchayet at SriKrishnapur Mouza (Node no. 300 to 307 to 314 to 320) of Raghunathpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000258/2024-2025 | 1029/BHTSD | 28/06/2024 | 05/07/2024 | M/S. WAY CON. | 0.91 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raghunathpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000746/2022-2023 | 3344/BD | 16/11/2022 | 14/02/2023 | UTPAL CONSTRUCTION & CO. | 180.46 | 155.48 | 86.15 | 88
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Raghunathpur to accommodate FHTC | SM/11628 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2022-2023 | 493/BD | 17/02/2023 |  | Resource Division | 10.73 | 0 | 0 | 0
Total | [13 empty] | 275.41 | 178.22 | 64.71