## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | SM/11629 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 488/BD | 17/02/2023 | 17/02/2023 | Resource Division | 57.91 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | SM/11629 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | SM/11629 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Eojnagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2024-2025 | 3257/BD | 25/11/2024 | 23/02/2025 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Eojnagar to accommodate FHTC | SM/11629 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Eojnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2022-2023 | 3603/BD | 09/12/2022 | 25/08/2025 | KINGS & CO. | 361.31 | 0 | 0 | 74
Total | [13 empty] | 21780.74 | 0 | 0