## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | Augmentation | Route Survey, Design Drawing & DPR Preparation for RAJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002780/2021-2022 | 208/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.72 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Rajnagar water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 3587/BD | 08/12/2022 | 07/01/2023 | B.S.ENTERPRISE. (BASIRHAT) | 62.54 | 0 | 0 | 100
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 485/BD | 17/02/2023 | 17/02/2023 | Resource Division | 0.44 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/003332/2023-2024 | 4809./EMD | 09/08/2023 | 08/09/2023 | S.G. ENTERPRISE | 65.16 | 0 | 0 | 75
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Rajnagar to accommodate FHTC | SM/11630 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.- II under Rajnagar ground water based water supply scheme under Block_ Basirhat-II Dist. - 24 PARAGANAS (N) under EMD, PHE Dte. [SM/11630] | Assistant Engineer |  | ORD/000652/2024-2025 | 2689/EMD | 20/11/2024 | 20/12/2024 | S M ELECTRICALS | 6.98 | 0 | 0 | 0
Total | [13 empty] | 137.84 | 0 | 0