## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002789/2021-2022 | 122/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 3.77 | 99.39 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 3685/BD | 14/12/2022 | 14/12/2022 | Resource Division | 117.82 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 3659/BD | 13/12/2022 | 13/12/2022 | Resource Division | 21.27 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kalupur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000954/2022-2023 | 93/BD | 11/01/2023 | 26/03/2026 | M/S S.S.ENTERPRISE. (SOUTH) | 454.09 | 407.31 | 89.7 | 90
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Shimulpur W/S Scheme and Pump House No-I and II (Rep.) under Ichapur W/S Scheme and Kalupur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 4798/EMD | 09/08/2023 | 08/09/2023 | ORIENTAL ENGINEERING CO. | 91.05 | 24.26 | 26.64 | 80
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kalupur Water Supply Scheme (H/W Site & 2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001111/2023-2024 | 2924/BD | 26/09/2023 | 25/11/2023 | SAHA CONSTRUCTION & CO | 32.29 | 25.26 | 78.23 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000350/2024-2025 | 2417/BD | 23/08/2024 | 22/10/2024 | ROY CHOWDHURY CONSTRUCTION. | 37.8 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001751/2023-2024 | 562/BD | 22/02/2024 | 07/04/2024 | RAJ ENTERPRISE. | 7.53 | 7.52 | 99.78 | 100
9 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC | SM/11631 | Augmentation | Acceptance cum work order for Construction of Boundary wall at 1st Tube well site for Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001744/2023-2024 | 560/BD | 22/02/2024 | 07/04/2024 | MA CONSTRUCTION. | 9.33 | 9.31 | 99.76 | 100
Total | [13 empty] | 774.98 | 477.42 | 61.6