## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for Providing Functional tap connection at Paschim Monipur FP School, East Monipur Khargeswar Adibasi FP School within the command area of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000865/2023-2024 | 1051/HSD | 31/08/2023 | 07/09/2023 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.48 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000846/2023-2024 | 2654/BD | 01/09/2023 | 01/10/2023 | M/S K.B.ENTERPRISE. | 27.43 | 27.39 | 99.87 | 85
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Monipur water supply scheme,Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000522/2022-2023 | 2446/BD | 23/08/2022 | 21/11/2022 | APURBA MANDAL | 278.15 | 252.56 | 90.8 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 1206/BD | 20/04/2023 | 20/05/2023 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 31.03 | 24.86 | 80.12 | 51
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001294/2023-2024 | 1416/HSD | 06/11/2023 | 13/11/2023 | BADAL GHOSH. | 0.97 | 0.97 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 2473/BD | 24/08/2022 | 24/08/2022 | Resource Division | 13.91 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 2474/BD | 18/08/2023 | 17/09/2023 | M/S RAJPATH CONSTRUCTION. | 31.64 | 25.14 | 79.47 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Monipur water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001291/2023-2024 | 1413/HSD | 06/11/2023 | 13/11/2023 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0.9 | 98.86 | 100
9 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) with Pump House no-III(New) under Monipur W/S Scheme with Bajitpur (I and II, Zone-II) W/S Scheme in District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001916/2023-2024 | 6739/EMD | 29/11/2023 | 01/07/2025 | GLACIER ENGINEERING CO. | 67.8 | 15.05 | 22.19 | 40
10 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Korakati and Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000775/2024-2025 | 3333/BD | 28/11/2024 | 27/01/2025 | UTPAL CONSTRUCTION & CO. | 63.34 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Monipur to accommodate FHTC | SM/11632 | Augmentation | Formal work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Monipur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 1721/BD | 08/06/2023 | 11/03/2025 | R.K.MANDAL & CO. | 150.42 | 127.83 | 84.99 | 90
Total | [13 empty] | 666.06 | 474.71 | 71.27