## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Gotra W/S Scheme District of 24 Pgs. (N). (SM/11633) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 09) |  |  | ORD/000555/2022-2023 | 6384/EMD | 24/11/2022 | 24/12/2022 | JOYSHREE CONCERN | 12.98 | 9.69 | 74.68 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (Replacement) under Gotra W/S Scheme District of 24 Pgs. (N). (SM/11633) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 10) |  |  | ORD/000558/2022-2023 | 6385/EMD | 24/11/2022 | 24/12/2022 | KASHINATH PAL & CO. | 13.05 | 11.42 | 87.53 | 0
3 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Gotra W/S Scheme (T/W-I), Basirhat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. (2ed Call) | Driller In Charge | Junior Engineer | ORD/000164/2023-2024 | 509/CDD | 01/06/2023 | 01/07/2023 | UNIVERSAL ENTERPRISES | 19.93 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2022-2023 | 487/BD | 17/02/2023 | 17/02/2023 | Resource Division | 237.82 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2022-2023 | 609/BD | 23/02/2023 | 23/02/2023 | Resource Division | 19.95 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gotra water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000789/2022-2023 | 3547/BD | 06/12/2022 | 06/03/2023 | BALAJI UDDYOG | 468.63 | 330.73 | 70.57 | 57
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Gotra water supply scheme under Basirhat Sub-Division, P.H.E.Dte. |  |  | BILL/01246/2024-2025 | BP-2024-25-393 | 04/10/2024 | 04/10/2024 | BALAJI UDDYOG | 16 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Gotra to accommodate FHTC | SM/11633 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Gotra Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000774/2024-2025 | 3264/BD | 25/11/2024 | 25/03/2025 | JOY GURU ENTERPRISE | 21.74 | 0 | 0 | 100
Total | [13 empty] | 810.11 | 351.84 | 43.43