## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Bansjhari Mallikpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000743/2022-2023 | 3341/BD | 16/11/2022 | 01/04/2025 | UTPAL CONSTRUCTION & CO. | 227.32 | 169.23 | 74.44 | 90
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 3813/BD | 23/12/2022 | 23/12/2022 | Resource Division | 98.04 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Bansjhari-Mullickpur and Maminpur W/S Scheme with Pump House No-I under Rajnagar W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/003332/2023-2024 | 4809./EMD | 09/08/2023 | 08/09/2023 | S.G. ENTERPRISE | 65.16 | 21.9 | 33.62 | 75
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 4415/BD | 10/11/2023 | 10/11/2023 | Resource Division | 9.24 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Bansjhari Mallickpur to accommodate FHTC | SM/11634 | Augmentation | Acceptance cum work order for for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Bansjhari Mallikpur Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase -I). |  |  | BILL/01926/2025-2026 |  | 18/11/2025 | 18/11/2025 | SUDHAMAY MAJUMDAR. | 2.59 | 0 | 0 | 0
Total | [13 empty] | 21742.11 | 191.13 | 0.88