## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Replacement) under Pipha W/S Scheme District of 24 Pgs. (N). (SM/11635) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 15) |  |  | ORD/000566/2022-2023 | 6389/EMD | 24/11/2022 | 24/12/2022 | C.M.S. ENGINEERING CONCERN. | 13.05 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III (Replacement) under Pipha W/S Scheme District of 24 Pgs. (N). (SM/11635) NIET No.- 19 of EE/EMD of 2022-23 (Sl. No.- 17) |  |  | ORD/000570/2022-2023 | 6391/EMD | 24/11/2022 | 24/12/2022 | SANKAR PROSAD DUTTA & CO. | 13.02 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | : Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 270 Mtrs. Depth) by utilising Departmental Machineries for Pipha W/S Scheme (TW-I), Barasat-I Block under North 24 Pgs. District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000155/2023-2024 | 1653/CDD | 17/10/2023 | 16/11/2023 | UNIVERSAL ENTERPRISES | 19.87 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2022-2023 | 495/BD | 17/02/2023 | 17/02/2023 | Resource Division | 44.41 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2022-2023 | 599/BD | 23/02/2023 | 23/02/2023 | Resource Division | 7.47 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 4423/BD | 10/11/2023 | 10/11/2023 | Resource Division | 6.16 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Pipha water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000842/2022-2023 | 3631/BD | 12/12/2022 | 06/02/2025 | SANDIP BISWAS | 318.65 | 0 | 0 | 95
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Pipha to accommodate FHTC | SM/11635 | Augmentation | Acceptance cum work order for Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Pifa water Supply Scheme within Basirhat - I Block under Basirhat Sub-Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2024-2025 | 3131/BD | 12/11/2024 | 11/05/2025 | M/S MITRA CONSTRUCTION. | 49.39 | 0 | 0 | 100
Total | [13 empty] | 472.02 | 0 | 0