## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1249/BD | 25/04/2023 | 25/04/2023 | Resource Division | 114.4 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 4406/BD | 10/11/2023 | 10/11/2023 | Resource Division | 15.4 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep.) under Sankchura W/S Scheme and Paschim Madhyampur W/s Scheme District of 24 Pgs. (N) |  |  | ORD/001165/2023-2024 | 4815/EMD | 09/08/2023 | 08/09/2023 | CONCORD ENGINEERING | 79.5 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Special repairing of pipe line at different location of Sankhchura Water Supply Scheme under Basirhat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 914/BHTSD | 24/05/2024 | 31/05/2024 | SOUMIT CONSTRUCTION | 0.31 | 0.31 | 100 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 385/BD | 07/02/2024 | 07/02/2024 | Resource Division | 65.63 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sankchura water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 1708/BD | 08/06/2023 | 31/05/2025 | UTPAL CONSTRUCTION & CO. | 444.98 | 311.93 | 70.1 | 50
7 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sankchura Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2024-2025 | 3255/BD | 25/11/2024 | 25/03/2025 | M/S K.P.PAL. | 21.75 | 0 | 0 | 100
8 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Sankchura to accommodate FHTC | SM/11653 | Augmentation | Acceptance cum work order for Restoration of roads from Sankchura Godown more towards Katarati more within Nimderia Kodalia GP under Sankchura Water Supply Scheme of Basirhat-I Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002165/2024-2025 | 1023/BD | 28/03/2025 | 27/05/2025 | SUPER ENTERPRISE | 7.09 | 0 | 0 | 100
Total | [13 empty] | 749.06 | 312.24 | 41.68