## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Masia Nabastia water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000747/2022-2023 | 3372/BD | 18/11/2022 | 16/02/2023 | GHOSH CONSTRUCTION. | 146.63 | 126.32 | 86.15 | 85
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 492/BD | 17/02/2023 | 17/02/2023 | Resource Division | 12.12 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 2307/BD | 03/08/2022 | 03/08/2022 | Resource Division | 12.12 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Acceptance cum work order for balance works of Augmentation (including FHTC) within the command area of Masia and Nabastya Piped Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000698/2024-2025 | 3185/BD | 18/11/2024 | 14/10/2025 | GHOSH CONSTRUCTION. | 32.23 | 0 | 0 | 80
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Permanent restoration of damaged / top be damaged black top surface hard shoulder from 0.00kmp to 6.70km (damaged incurred / to be incurred due to laying of PHE pipe line by Barasat Arsenic Division PHED from 0.20KM TO 6.70KM (R/H) & Barasat Division PHED from 1.00km to 3.30kM (L/S) &5.20km to 6.00 km (L/S) OF Ramchandrapur Baduria road, for laying 250mm dia DI Primary rising main and 140mm to 90mm dia UPVC distribution line for integrated surface water based piped water supply scheme for arsenic affected blocks under Barasat Highway Division NO-I in the District of North 24 Parganas. |  |  | BILL/01548/2024-2025 | BP-2024-25-478 | 22/01/2025 | 22/01/2025 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 10.37 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21553.23 | 126.32 | 0.59