## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Masia Nabastia water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000747/2022-2023 | 3372/BD | 18/11/2022 | 16/02/2023 | GHOSH CONSTRUCTION. | 146.63 | 0 | 0 | 85
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2022-2023 | 492/BD | 17/02/2023 | 17/02/2023 | Resource Division | 12.12 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 2307/BD | 03/08/2022 | 03/08/2022 | Resource Division | 12.12 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Masia Nabastia to accommodate FHTC | SM/11654 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21510.63 | 0 | 0