## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2022-2023 | 3816/BD | 23/12/2022 | 23/12/2022 | Resource Division | 119.56 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000179/2022-2023 | 610/BD | 23/02/2023 | 23/02/2023 | Resource Division | 10.1 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 4408/BD | 10/11/2023 | 10/11/2023 | Resource Division | 6.16 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Magurali water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000744/2022-2023 | 3342/BD | 16/11/2022 | 27/07/2025 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 567.42 | 0 | 0 | 71
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Magurali and its adjoining mouzas to accommodate FHTC | SM/11655 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery along with allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Magurali and P.H. No.- II under Chandipur W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001270/2023-2024 | 4935/EMD | 18/08/2023 | 17/09/2023 | SUNRISE ENGINEERING CORPORATION | 39.08 | 0 | 0 | 0
Total | [13 empty] | 742.32 | 0 | 0