## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Patua Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002755/2021-2022 | 444/ BHTSD | 22/03/2022 | 06/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.16 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000180/2022-2023 | 601/BD | 23/02/2023 | 23/02/2023 | Resource Division | 6.94 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000201/2022-2023 | 859/BD | 20/03/2023 | 20/03/2023 | Resource Division | 48.85 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Replacement) under Bharatpur W/S Scheme, Patua W/S Scheme (P/H-I & II) & Chaital W/S Scheme (P/H -I & II) District of 24 Pgs. (N). NIET No. 24 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000824/2022-2023 | 31/EMD | 03/01/2023 | 01/04/2025 | M/S P.P. ELECTRICALS | 74.67 | 15.43 | 20.67 | 73
5 | NORTH 24 PARGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Patua Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000787/2022-2023 | 3549/BD | 06/12/2022 | 25/10/2025 | SUBHASH BOSE. | 326.66 | 224.76 | 68.8 | 27
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Patua to accommodate FHTC | SM/11656 | Augmentation | Providing outdoor illumination arrangement at P.H. No. I under Patua W/S Scheme under EMSD-I, P.H.E.Dte. Dist.- 24PGS(N). | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 456/EMSD-I | 08/04/2025 | 31/05/2025 | C.N. ENTERPRISE | 1.36 | 0 | 0 | 100
Total | [13 empty] | 462.66 | 244.35 | 52.81